|  |  |  |  |
| --- | --- | --- | --- |
|  | Code | Task | Days |
| 1 | Demo | Site Prep Demo | 5 days |
| 2 | MAS | Footers and Foundation | 10 days |
| 3 | FR | Framing | 10 days |
| 4 | R | Roofing | 2 days |
| 5 | FG | Final Grade / Landscaping | 3 days |
| 6 | EWD | Windows and Exterior Doors | 1 day |
| 7 | SF | Soffit and Fascia | 3 days |
| 8 | SIDE | Siding and Exterior Trim | 5 days |
| 9 | EP | Exterior Paint | 2 days |
| 10 | GTR | Gutters and Downspouts | 1 day |
| 11 | ELR | Electrical Rough In | 3 days |
| 12 | PLR | Plumbing Rough In | 3 days |
| 13 | HR | HVAC Rough In | 2 days |
| 14 | I | Insulation Install | 1 day |
| 15 | D | Drywall Rough In | 5 days |
| 16 | M | Mud, Prime, Texture | 10 days |
| 17 | IP | Interior Paint | 2 days |
| 18 | FL  | Flooring | 5 days |
| 19 | CB | Cabinets /Countertops | 1 day |
| 20 | T | Interior Doors and Trim | 5 days |
| 21 | ELF | Electrical Finish | 2 day |
| 22 | PLF | Plumbing Finish | 2 day |
| 23 | HF | HVAC Finish | 1 day |
| 24 | FP | Final Punch | 3 days |
| 25 | FC | Final Clean | 2 days |
| 26 | H | Hold |  |