## 4.05.12-2.15.13
CLIENT NAME |  | ROGER M. | [6 empty] | BOBBY BURTON |  |  |  |  | TARA J. | [6 empty] | DAVID D. | [5 empty] | WES L. | [6 empty] | DAN F. | [6 empty] | ED & TAMMY MOORE | [6 empty] | HAZEL G. |  |  |  |  | TAMMY N. |  |  |  |  | MICHAEL J. | [6 empty] | EARL W. | [5 empty] | LARRY H. |  |  |  |  | SUSAN I. |  |  |  |  | GREG L. |  |  | BRIAN FARLEY | [5 empty] | SUSAN HENSEN | [6 empty] | CATHERINE LACASCIO |  |  |  |  | VIVIAN PENDERGRAFF |  |  |  | KASI MALLET |  |  | RHONDA WRIGHT |  |  |  |  | NANCY LEONARD |  |  |  |  | REBECCA SMITH |  |  |  |  | PAMELA McREYNOLDS |  |  |  |  | MATTHEW BECK |  |  | DONNA B. |  |  |  |  | TARA J. | [6 empty] | AMBER B. | [5 empty] | SUSAN D. |  |  |  | EDITH O. | [6 empty] | TIMOTHY P. | [5 empty] | BRENDA HATFIELD | [5 empty] | PAUL E. | [6 empty] | BETTY C. |  |  | BRANDON S. |  |  | AUTUMN T |  |  | BRANDY S. |  |  |  | RAYMOND B. |  |  |  |  | CLAY M. |  |  |  |  | JAMIE P. |  |  |  |  | DAMON M. |  |  |  |  | OLLIE S. |  |  |  |  | KEN C. |  |  |  |  | DIANA J.
ADDRESS |  | 2839 E. 18TH | [6 empty] | 1016 WEST 19TH |  |  |  |  | 2021 JACKSON | [6 empty] | 2501 ANNIE BAXTER | [5 empty] | 1901 ILLINOIS | [6 empty] | 2206 KENTUCKY | [6 empty] | 2121 SOUTH WALL | [6 empty] | 2202 CONNOR | [9 empty] | 2325 BYERS | [25 empty] | 614 S. MCKINLEY | [5 empty] | 125 NORTH MAPLE | [6 empty] | 1298 COUNTY LANE 176 |  |  |  |  | 1730 PEARL STREET |  |  |  | 5053 E. 22ND |  |  | 2328 S. WILLIARD |  |  |  |  | 1206 KATHERINE |  |  |  |  | 2006 PENNSYLVANIA |  |  |  |  | 1726 MISSOURI |  |  |  |  | 1216 S. MURPHY |  |  | 2422 PENNSYLVANIA |  |  |  |  | 2021 JACKSON | [6 empty] | 10345 OLD SCENIC RD | [5 empty] | 2127 S. MOFFET |  |  |  | 1709 MISSOURI | [6 empty] | 1805 W. 22ND | [5 empty] | 1320 S. PRIGMORE | [5 empty] | 2621 S. CONNOR | [6 empty] | 737 PLAZA DR. |  |  | 1401 MINNESOTA |  |  | 715 HILL ST. |  |  | 2633 S. BYERS |  |  |  | 1731 S. MURPHY |  |  |  |  | 2024 W. 26TH |  |  |  |  | 2214 S. HIGHVIEW |  |  |  |  | 106 FOX -- ALBA, MO |  |  |  |  | 301 S. FLORIDA |  |  |  |  | 2206 EMPIRE |  |  |  |  | 1921 S. EMPIRE
BUILDING PERMIT |  | 12-2008 | [6 empty] | 12-1811 |  |  |  |  | 12-2006 | [6 empty] | 12-2279 | [5 empty] | 12-2302 | [6 empty] | 11-3525 | [13 empty] | 12-1030 | [9 empty] | 11-4726 | [25 empty] | 12-1810 | [5 empty] | 12-1906 | [6 empty] | N/A | [8 empty] | RR 12-006 |  |  | 12-1807 |  |  |  |  | N/A |  |  |  |  | 12-18008 |  |  |  |  | 12-1809 |  |  |  |  | 12-2030 |  |  | 12-1526 |  |  |  |  | 12-2006 | [6 empty] | N/A | [9 empty] | 12-2492 | [6 empty] | 12-2493 | [11 empty] | 12-2542 | [6 empty] | N/A |  |  | 13-0140 |  |  | 12-2314 |  |  | 13-0194 | [8 empty] | 11-4292 | [24 empty] | 13-0222
PROJECT MANAGER |  | Darrell Kelley | [11 empty] | Darrell Kelley | [6 empty] | Darrell Kelley | [12 empty] | Brad Mudge | [23 empty] | Brad Mudge | [17 empty] | Brad Mudge | [7 empty] | Brad Mudge | [44 empty] | Brad Mudge |  |  | Darrell Kelley |  |  |  |  | Darrell Kelley | [16 empty] | Darrell Kelley
SITE SUPERVISOR | [153 empty] | Zach Bozeman
CLIENT SERVICES |  | N/A | [151 empty] | Brittany Kennell
NEW/REMODEL |  | New | [151 empty] | New
| VOLUNTEER # | Projected |  |  | Actual |  |  | Volunteers | Projected |  | Actual |  | Volunteers | Projected |  |  | Actual |  |  | Volunteers | Projected |  |  | Actual |  | Volunteers | Projected |  |  | Actual |  |  | Volunteers | Projected |  |  | Actual |  |  | Volunteers | Projected |  |  | Actual |  |  | Volunteers | Projected |  | Actual |  | Volunteers | Projected |  | Actual |  | Volunteers | Projected |  |  | Actual |  |  | Volunteers | Projected |  |  | Actual |  | Volunteers | Projected |  | Actual |  | Volunteers | Projected |  | Actual |  | Volunteers | Projected | Actual | Volunteers | Projected |  |  | Actual |  | Volunteers | Projected |  |  | Actual |  |  | Volunteers | Projected |  |  | Actual | Volunteers | Projected |  | Actual | Volunteers | Projected | Actual | Volunteers | Projected |  | Actual |  | Volunteers | Projected |  | Actual |  | Volunteers | Projected |  | Actual |  | Volunteers | Projected |  | Actual |  | Volunteers | Projected | Actual | Volunteers | Projected |  | Actual |  | Volunteers | Projected |  |  | Actual |  |  | Volunteers | Projected |  |  | Actual |  | Volunteers | Projected | Actual |  | Volunteers | Projected |  |  | Actual |  |  | Volunteers | Projected |  | Actual |  |  | Volunteers | Projected |  | Actual |  |  | Volunteers | Projected |  |  | Actual |  |  | Volunteers | Projected | Actual | Volunteers | Projected | Actual | Volunteers | Projected | Actual | Volunteers | Projected |  | Actual | Volunteers | Projected |  | Actual |  | Volunteers | Projected |  | Actual |  | Volunteers | Projected |  | Actual |  | Volunteers | Projected |  | Actual |  | Volunteers | Projected |  | Actual |  | Volunteers | Projected |  | Actual |  | Volunteers | Projected | Actual | Volunteers
2012-04-05 | [33 empty] | Site | FR |  | Site | FR |  |  | FL | T |  | FL | T |  |  | FR |  | FR | [14 empty] | Demo |  |  | Demo
2012-04-06 | [33 empty] | Site | FR |  | Site | FR |  |  | FL | T |  | FL | T |  |  | FR |  | FR | [14 empty] | Demo |  |  | H
2012-04-07 | [33 empty] | Site | I |  | Site |  |  |  | FL | T | PLR | FL | T | PLR |  | FR |  | FR | [14 empty] | Demo |  |  | H
2012-04-08 | [33 empty] | Site | I | D | 0 |  |  |  | FL | T | PLR | FL | T | PLR |  | HR | PLR | FR | PLR | [13 empty] | H |  |  | H
2012-04-09 | [33 empty] | Site | I | D | 0 |  |  |  | FL | T | PLR | FL | T | PLR |  | PLR | ELR | PLR | ELR |  | MAS |  | MAS | [9 empty] | H |  |  | H
2012-04-10
2012-04-11
2012-04-12 | [33 empty] | I | D | M | 0 |  |  |  | CB | CT |  | T |  |  |  | PLR | ELR | PLR | ELR |  | MAS |  | MAS |  |  | FR | PLR | MAS | MAS |  |  |  | Demo |  |  | ELR |  |  | FL |  | T | [7 empty] | Demo | Demo
2012-04-13 | [33 empty] | D | M |  | I |  |  |  | CB | CT |  | T |  |  |  | PLR | ELR | PLR | ELR |  | MAS |  | MAS |  |  | FR | MAS |  | FR | MAS |  |  | Demo |  |  | 0 |  |  | FL |  | ELF | [7 empty] | Demo | FR
2012-04-14
2012-04-15
2012-04-16 | [33 empty] | D | M |  | D |  |  |  | FL | PLR |  | T | PLR |  |  | PLR | ELR |  |  |  | MAS | FR | MAS | FR |  | MAS |  |  | 0 |  |  |  | I | FR |  | 0 |  |  | FL |  | FL | [7 empty] | Side | Side
2012-04-17 | [33 empty] | D | M |  | D |  |  |  | FL | PLF |  | T | PLF |  |  | I |  | I |  |  | MAS | FR | MAS | FR |  | MAS |  |  | MAS |  |  |  | I | D |  | Demo |  |  | FL |  | FL | [7 empty] | Side | Side
2012-04-18 | [33 empty] | D | M |  | D |  |  |  | FL | PLF |  | T | PLF |  |  | I |  | I |  |  | MAS | FR | MAS | FR | [8 empty] | I | D |  | FR |  |  | HOLD |  |  |  |  | Demo |  | Demo |  |  | Side | 0
2012-04-19 | [33 empty] | M |  |  | D |  |  |  | T |  |  | T |  |  |  | D |  | I | D |  | Demo |  | 0 | [9 empty] | D | M |  | H |  |  | HOLD |  |  |  |  | Demo |  | Demo |  |  | Side | Side
2012-04-20 | [33 empty] | M |  |  | M |  |  |  | HOLD |  |  | HOLD |  |  |  | D |  | D |  |  | I | D | 0 | [9 empty] | D | M |  | H |  |  | HOLD |  |  |  |  | FR |  | 0 |  |  | Side | 0
2012-04-21
2012-04-22
2012-04-23 | [33 empty] | M |  |  | M |  |  |  | HOLD |  |  | HOLD |  |  |  | D |  | D |  |  | D | M | 0 | [9 empty] | M |  |  | H |  |  | HOLD |  |  |  |  | FR |  | 0 |  |  | Side | 0
2012-04-24 | [33 empty] | M |  |  | M |  |  |  | HOLD |  |  | HOLD |  |  |  | D | M | D | M |  | M |  | 0 | [9 empty] | M |  |  | H |  |  | HOLD |  |  |  |  | FR |  | 0 |  |  | Side | 0
2012-04-25 | [33 empty] | M |  |  | M |  |  |  | HOLD |  |  | HOLD |  |  |  | D | M | M |  |  | M |  | 0 | [9 empty] | M |  |  | H |  |  | HOLD |  |  |  |  | FR |  | 0 |  |  | Side | 0
2012-04-26 | [33 empty] | M |  |  | M |  |  |  | HOLD |  |  | HOLD |  |  |  | D | M |  |  |  | MAS | FR | MAS | FR | [8 empty] | IP |  |  |  |  | 7 | HOLD |  |  |  |  | Demo |  | Demo |  |  | Side | 0 | 12
2012-04-27 | [33 empty] | M |  |  | M |  |  | 20 | HOLD |  |  | HOLD |  |  |  | M |  |  |  |  | MAS | FR | MAS | FR | [8 empty] | IP |  |  |  |  | 7 | HOLD |  |  |  |  | Demo |  | Demo | FR |  | Side | 0 | 12
2012-04-28 | [33 empty] | M |  |  | M |  |  | 12 | PLR | [5 empty] | 2 | M |  |  |  |  | FR | M | FR | M | [8 empty] | IP | T |  |  |  | 7 | HOLD |  |  |  |  | FR |  | FR |  |  | Side | 0 | 12
2012-04-29 | [33 empty] | M |  |  | M |  |  | 12 | CB | CT | [5 empty] | M |  | M |  |  | Side | M | Side | M | [8 empty] | T |  |  |  |  | 5 | HOLD |  |  |  |  | FR |  | FR | R |  | Side | 0 | 12
2012-04-30 | [33 empty] | M |  |  | M |  |  | 12 | HR | [6 empty] | M |  | M |  |  | Side | IP | Side | IP | [14 empty] | HOLD |  |  |  |  | FR |  | FR | R |  | Side | 0 | 12
2012-05-01
2012-05-02 | [33 empty] | M |  |  | M |  |  | 12 | CB |  |  | 0 |  |  | 6 | M |  | 0 |  |  | IP |  | 0 |  |  | ELR | PLR | FR | ELR | PLR | FR | 22 | FR |  |  | H |  | 6 | FL |  | FL |  | 1 | HOLD |  | HOLD |  |  | Side | Side | 12
2012-05-03 | [33 empty] | M |  |  | M |  |  | 12 | CB |  |  | CB |  |  | 6 | M |  | M |  | 8 | T | FL | IP |  | 4 | ELR | PLR | FR | ELR | PLR | FR | 22 | FR |  |  | FR |  | 6 | T | ELF | T | ELF | 3 | HOLD |  | HOLD |  |  | Side | Side | 12
2012-05-04 | [33 empty] | M |  |  | M |  |  | 12 | CB |  |  | CB |  |  | 6 | M |  | 0 |  |  | T | FL | 0 |  | 4 | ELR | PLR | FR | ELR | PLR | FR | 22 | I | D |  | FR | I | 6 | T | ELF | 0 |  | 0 | HOLD |  | HOLD |  |  | Side | Side | 12
2012-05-05 | [33 empty] | M |  |  | M |  |  | 12 | FL | [5 empty] | 6 | M |  | 0 |  | 8 | HOLD |  | 0 |  | 4 | ELR | FR |  | ELR | FR |  | 8 | D |  |  | D |  | 6 | FC |  | 0 |  | 0 | HOLD |  | HOLD |  |  | Side | Side | 12
2012-05-06 | [33 empty] | IP |  |  | 0 |  |  | 12 | FL | [5 empty] | 6 | IP |  | 0 |  | 8 | HOLD |  | 0 |  | 4 | FR | [5 empty] | 10 | D | M |  | 0 |  | 6 | FP |  | 0 |  | 2 | HOLD |  | HOLD |  |  | Side | 0 | 12
2012-05-07
2012-05-08
2012-05-09 | [33 empty] | IP |  |  | M |  |  | 12 | FL |  |  | CB |  |  | 6 | IP |  | M | IP | 8 | IP |  | IP |  | 4 | I | D |  | FR |  |  | 8 | M |  |  | 0 |  | 6 | [5 empty] | Side | ELR | 0 |  |  | T | T | 6
2012-05-10 | [33 empty] | IP |  |  | IP |  |  | 12 | FL |  |  | CB |  |  | 6 | IP |  | IP |  | 8 | T | FL | T | FL | 4 | I | D |  | FR |  |  | 8 | M |  |  | D |  | 6 | [5 empty] | Side | ELR | 0 |  | 7 | T | T | 6
2012-05-11 | [33 empty] | IP |  |  | IP |  |  | 12 | T | FL |  |  |  |  | 3 | IP | FL | IP |  | 8 | T | FL | 0 |  | 4 | D |  |  | FR |  |  | 8 | M |  |  | D |  | 6 | [5 empty] | Side | ELR | 0 |  | 7 | T | T | 6
2012-05-12 | [33 empty] | FL |  |  | IP |  |  | 12 | FP |  |  | FL |  |  | 3 | FL | T | IP |  | 8 | [5 empty] | D | M |  | FR |  |  | 8 | IP |  |  |  |  | 6 | [5 empty] | Side | I |  |  | 7 | FP | T | 6 | FL |  |  | FL |  |  | M |  |  | M |  |  | 10
2012-05-13 | [33 empty] | FL | T |  | 0 |  |  | 12 | FP | [5 empty] | 3 | FL | T |  |  | 8 | [5 empty] | M | [5 empty] | 8 | IP | T |  |  |  | 6 | [5 empty] | Side | I |  |  | 7 | FC |  | 6 | FL |  |  | FL |  |  | M |  |  | M |  |  | 10
2012-05-14
2012-05-15
2012-05-16 | [33 empty] | FL | T |  |  |  |  | 12 | FC | [5 empty] | 5 | FL | T | [8 empty] | M | [5 empty] | 8 | T |  |  |  |  | 6 | [5 empty] | D |  | 0 |  | 8 | T |  |  | FL |  |  | FL |  |  | M |  |  | IP |  |  | 10
2012-05-17 | [33 empty] | FL | T |  |  |  |  | 12 | [7 empty] | PLF | ELF | [8 empty] | M | [5 empty] | 8 | FC |  |  |  |  | 6 | [5 empty] | D |  | 0 |  | 8 | T |  |  | FL |  |  | FL |  |  | IP |  |  | IP |  |  | 10
2012-05-18 | [33 empty] | FL | T |  |  |  |  | 12 | [7 empty] | PLF | ELF | [8 empty] | M | [5 empty] | 8 | M | [10 empty] | D | M |  |  | 8 | ELF |  |  | CB | CT |  | CB |  | 4 | IP | FL |  | FL | T |  | 10
2012-05-19 | [33 empty] | FL | T |  |  |  |  | 12 | [7 empty] | PLF | ELF | [8 empty] | M | [5 empty] | 8 | M | [10 empty] | M |  |  |  | 8 |  |  |  | CB | CT |  | CB |  | 4 | FL | T | ELF | CB |  |  | 10
2012-05-20 | [33 empty] | FL | T |  |  |  |  | 12 | [7 empty] | CB | CT | [8 empty] | M | [5 empty] | 8 | M | [10 empty] | M |  |  |  | 8 |  |  |  | CB | CT |  | CB | CT | 4 | T | ELF | CB | FL | CB |  | 10
2012-05-21
2012-05-22
2012-05-23 | [8 empty] | M |  |  |  | 2 | [20 empty] | CB | CT |  |  |  |  | 6 | [7 empty] | CB | CT | [8 empty] | FL | [5 empty] | 6 | FR | M |  | FR | M | [6 empty] | M | [7 empty] | FL | PLF |  |  |  | 4 | CB | PLF | Side | CB | PLF | Side | 24 | FL | T |  |  | 16 |  |  |  |  | R |  | 5
2012-05-24 | [33 empty] | CB | CT |  |  |  |  | 6 | [7 empty] | CB | CT | [8 empty] | FL | [5 empty] | 6 | FR | M | IP | [8 empty] | IP | [7 empty] | FL | PLF | Side |  |  | 18 | PLF | Side |  |  |  |  | 24 | FL | T |  |  | 16 | ELR |  |  | 1 | R |  | 5
2012-05-25 | [8 empty] | PLF |  |  |  | 10 | [20 empty] | CB | CT |  |  |  |  | 6 | [7 empty] | FP | [9 empty] | FL | T |  |  |  |  | 6 | M | IP | [9 empty] | IP | [7 empty] | Side |  |  |  |  | 14 | Side | [5 empty] | 14 | FL | T |  |  | 16 |  |  |  |  | R |  | 5
2012-05-26 | [8 empty] | PLF |  |  |  | 10 | [20 empty] | PLF | ELF |  |  |  |  | 4 | [7 empty] | FP | [9 empty] | FL | T |  |  |  |  | 6 | IP | [10 empty] | FL | [7 empty] | Side |  |  |  |  | 14 | Side | [5 empty] | 14 | FL | T |  |  | 16 | I |  |  | 6 | R |  | 5
2012-05-27 | [8 empty] | PLF |  |  |  | 10 | [20 empty] | PLF | ELF |  |  |  |  | 4 | [7 empty] | FC | [9 empty] | T | [5 empty] | 6 | T | FL | [9 empty] | FL | [7 empty] | Side |  |  |  |  | 14 | Side | [6 empty] | FL | T |  |  | 16 | I |  |  | 6 | R |  | 5
2012-05-28
2012-05-29 | [8 empty] | PLF |  |  |  | 10
2012-05-30 | [8 empty] | PLF |  |  |  | 3 | [20 empty] | PLF | ELF |  | RWK |  |  | 4 | [17 empty] | CB | CT |  |  |  |  | 6 | [11 empty] | T | [7 empty] | FP | FC |  |  |  |  | EP | FC | [5 empty] | ELF | CB |  |  | 8 | D |  |  | 16
2012-05-31 | [83 empty] | FC | [5 empty] | FC | [10 empty] | 8
2012-06-01 | [8 empty] | T | FL |  |  | 3 | [20 empty] | FP |  |  | RWK |  |  | 4 | [17 empty] | CB | CT |  |  |  |  | 6 | FL | [10 empty] | FP | [20 empty] | ELF | CB |  |  | 8 | D | M |  | 16
2012-06-02 | [8 empty] | T | FL |  |  | 3 | [20 empty] | FP |  |  | RWK |  |  | 4 | [17 empty] | CB | CT |  |  |  |  | 6 | [11 empty] | FP |  | D | [18 empty] | ELF | CB | CT |  | 8 | M |  |  | 16
2012-06-03 | [8 empty] | T | FL |  |  | 3 | [20 empty] | FP | [5 empty] | 4 | [17 empty] | PLF | ELF |  |  |  |  | 6 | [11 empty] | FP |  | D | M | [17 empty] | ELF | CB | CT |  | 8 | M |  |  | 16
2012-06-04 | [8 empty] | T | FL |  |  | 3 | [20 empty] | FC | [5 empty] | 12 | [17 empty] | PLF | ELF |  |  |  |  | 6 | [11 empty] | FL | [7 empty] | FR |  |  | Demo |  | 8 | [7 empty] | FC |  |  |  | 8 | IP |  |  | 16 | [8 empty] | FR |  | FR |  | 5 | SF |  | Demo |  | 5
2012-06-05 | [33 empty] | T | PLF | Side | [21 empty] | ELF | T |  |  |  |  | 5 | [11 empty] | PLF |  | PLF |  | 4 | [28 empty] | FR |  | FR |  | 5 | FR |  | FR |  | 5 | SF |  | Demo |  | 5
2012-06-06 | [33 empty] | T | PLF | Side | T |  |  | 6 | [17 empty] | ELF | T |  |  |  |  | 5 | [11 empty] | PLF |  | PLF |  | 4 |  |  |  | FR |  |  | HOLD |  | 8 | [19 empty] | FR |  | FR |  | 5 | FR |  | FR |  | 5 | SF |  | Demo |  | 5
2012-06-07 | [33 empty] | T |  |  | ELF | HF | T | 6 | [17 empty] | FL | T |  |  |  |  | 5 | [11 empty] | SF |  | PLF |  | 4 |  |  |  | FR |  |  | HOLD |  | 8 | [19 empty] | FR |  | FR |  | 5 | FR |  | FR |  | 5 | SF |  | Demo |  | 5
2012-06-08 | [33 empty] | T |  |  | ELF | T |  | 6 | [17 empty] | FL | T |  |  |  |  | 5 | [11 empty] | SF |  | ELF |  | 4 |  |  |  | FR |  |  | HOLD |  | 8 | [19 empty] | FR |  | FR |  | 5 | FR |  | FR |  | 5 | SF |  | Demo |  | 5
2012-06-09 | [63 empty] | 5 | [48 empty] | 5
2012-06-10 | [63 empty] | 5
2012-06-11 | [33 empty] | CB |  |  | PLF |  |  | 6 | [17 empty] | T | FL |  |  |  |  | 5 | [11 empty] | ELF |  | ELF |  | 4 |  |  |  | FR |  |  | HOLD |  | 8 | [19 empty] | Demo |  | D |  |  | ELR |  | FR |  | 5 | Side |  | FR |  | 10 | Demo |  | Demo |  | 15
2012-06-12 | [33 empty] | CB |  |  | PLF |  |  | 6 | [17 empty] | PLF | [5 empty] | 5 | [11 empty] | FP |  | ELF |  | 4 |  |  |  | FR |  |  | HOLD |  | 8 | Demo | FR |  | Demo | FR | [14 empty] | FR |  | D | M |  | ELR | PLR | FR | ELR | 5 | Side |  | FR |  | 10 | Demo |  | Demo |  | 15
2012-06-13 | [33 empty] | CT |  |  | PLF | [20 empty] | CB | [5 empty] | 5 | [11 empty] | FP |  | FP |  | 4 |  |  |  | FR |  |  | HOLD |  | 8 | R |  |  | FR | [15 empty] | FR |  | D | M |  | ELR | PLR | ELR |  | 5 | Side |  | FR |  | 10 | Demo |  | Demo |  | 15
2012-06-14 | [33 empty] | T |  |  | T | PLF | [19 empty] | T | [5 empty] | 5 | [15 empty] | 4 |  |  |  | FR |  |  | HOLD |  | 8 | R |  |  | R | [15 empty] | ELR |  | M | FL |  | I |  |  |  | 8 | Side |  | FR |  | 10 | Demo |  | Demo |  | 15
2012-06-15 | [33 empty] | T |  |  | D | [20 empty] | CB | T |  |  |  |  | 5 | [15 empty] | 4 |  |  |  | FR |  |  | HOLD |  | 8 | R |  |  | R | [15 empty] | ELR |  | M | FL |  | I |  |  |  | 8 | Side |  | FR |  | 10 | Demo |  | Demo |  | 15
2012-06-16 | [57 empty] | CB | T |  |  |  |  | 5
2012-06-17
2012-06-18 | [33 empty] | R |  |  | ELF | PLF | T | 6 | [17 empty] | CB | T |  |  |  |  | 5 | [19 empty] | R |  |  | HOLD |  | 10 | Demo |  |  | R |  |  | 5 | [12 empty] | I |  | FL | M | 5 | D |  | FR | ELR | 8 | Side |  | Side |  | 10 | FR |  | FR |  | 10
2012-06-19 | [33 empty] | R |  |  | ELF | PLF | T | 6 | [17 empty] | CB | T |  |  |  |  | 5 | [19 empty] | R |  |  | HOLD |  | 10 | FR |  |  | R |  |  | 5 | [12 empty] | I |  | ELR | FL | 5 | D |  | FR | ELR | 8 | Side |  | Side |  | 10 | FR |  | FR |  | 10
2012-06-20 | [33 empty] | R |  |  | ELF | PLF | T | 6 | [17 empty] | CB | T |  |  |  |  | 5 | [19 empty] | R |  |  | HOLD |  | 10 | ELR |  |  | R |  |  | 5 | [12 empty] | D |  | ELR | FL | 5 | D |  | FR | ELR | 8 | Side |  | Side |  | 10 | FR |  | FR |  | 10
2012-06-21 | [33 empty] | R |  |  | ELF | PLF | T | 6 | [17 empty] | CB | T |  |  |  |  | 5 | [19 empty] | R |  |  | HOLD |  | 10 | I |  |  | 0 |  |  | 5 | [12 empty] | D |  | ELR |  | 5 | D |  | FR | ELR | 8 | Side |  | Side |  | 10 | FR |  | FR |  | 10
2012-06-22 | [33 empty] | R |  |  | ELF | PLF | T | 6 | [17 empty] | CB | T |  |  |  |  | 5 | [19 empty] | R |  |  | HOLD |  | 10 | D |  |  | 0 |  |  | 5 | [12 empty] | D |  | ELR | FL | 5 | D |  | FR | ELR | 8 | [5 empty] | FR |  | FR |  | 10
2012-06-23
2012-06-24
2012-06-25 | [33 empty] | SF | [5 empty] | 5 | [49 empty] | Demo |  |  | Demo |  |  | 5 | [12 empty] | FL |  | ELR | FL | 6 | Demo |  | Demo | ELR | 5 | Demo |  |  |  | 5
2012-06-26 | [33 empty] | SF | [5 empty] | 5 | [23 empty] | 5 | [25 empty] | Demo |  |  | 0 |  |  | 5 | [12 empty] | FL | T | FL | T | 6 | ELR |  | 0 |  | 5 | Demo |  |  |  | 5
2012-06-27 | [33 empty] | SF | [5 empty] | 5 | [23 empty] | 5 | [25 empty] | ELR |  |  | ELR |  |  | 5 | [12 empty] | T |  | FL | T | 5 | ELR |  | 0 |  | 5 | Demo |  |  |  | 5
2012-06-28 | [33 empty] | Side | [5 empty] | 5 | [17 empty] | RWK |  |  | RWK |  |  | 5 | [25 empty] | ELR |  |  | I | D |  | 5 | [12 empty] | T |  | FL | T | 5 | ELR |  | I |  | 5 | FR
2012-06-29 | [33 empty] | Side | [5 empty] | 5 | [17 empty] | RWK |  |  | 0 |  |  | 5 | [25 empty] | I |  |  | D |  |  | 5 | [12 empty] | Side |  | ELR | Side | 10 | ELR |  | I | D | 8 | FR
2012-06-30
2012-07-01
2012-07-02 | [33 empty] | T |  |  | T |  |  | 7 | [17 empty] | RWK |  |  | 0 |  |  | 5 | [11 empty] | FP |  | FP |  | 5 | [9 empty] | D |  |  | D |  |  | 6 | [12 empty] | Side |  | Side |  | 6 | I |  | D |  | 8 | ELR |  | ELR |  | 14 | SF |  | Side |  | 14
2012-07-03 | [33 empty] | T |  |  | T |  |  | 7 | [17 empty] | T |  |  | RWK |  |  | 5 | [11 empty] | FP |  | 0 |  | 5 | [9 empty] | D |  |  | M |  |  | 6 | [12 empty] | Side |  | Side |  | 6 | I |  | D |  | 8 | ELR |  | ELR |  |  | SF |  | Side |  | 14
2012-07-04 | [33 empty] | T |  |  | 0 | [20 empty] | T |  |  | RWK |  |  | 5 | [11 empty] | FP |  | 0 |  | 5 | [9 empty] | M |  |  | 0 |  |  | 6 | [12 empty] | Side |  | 0 |  | 6 | D |  | 0 |  | 8 | I |  | 0 |  |  | SF |  | Side |  | 14
2012-07-05 | [33 empty] | T |  |  | T |  |  | 7 | [17 empty] | T |  |  | RWK |  |  | 5 | [11 empty] | FP |  | FP |  | 5 | [9 empty] | M |  |  | IP |  |  | 6 | [12 empty] | FP |  | Side |  | 6 | D |  | D |  | 8 | I |  | D |  |  | SF |  | Side |  | 14
2012-07-06 | [33 empty] | T |  |  | T |  |  | 7 | [17 empty] | T |  |  | 0 |  |  | 5 | [11 empty] | FP |  |  |  | 5 | [9 empty] | M |  |  | RWK |  |  | 6 | [12 empty] | FC |  | FP |  | 6 | D |  | D | M | 8 | D |  |  |  |  | SF |  | Side |  | 14
2012-07-07
2012-07-08
2012-07-09 | [8 empty] | FR |  |  |  | 10 | [20 empty] | CB | [5 empty] | 4 | [17 empty] | PLF | [5 empty] | 5 | [11 empty] | CB |  |  |  | 20 |  |  |  | Demo |  |  |  |  | 20 | IP | [5 empty] | 6 | [17 empty] | M |  |  |  | 8 | D |  |  |  |  | Side |  |  |  | 14 | Demo |  | 13
2012-07-10 | [8 empty] | FR |  |  |  | 10 | [20 empty] | CB | [5 empty] | 4 | [17 empty] | PLF | [5 empty] | 5 | [11 empty] | CB |  |  |  | 20 |  |  |  | Demo |  |  |  |  | 20 | IP | [5 empty] | 6 | [17 empty] | M |  |  |  | 8 | M |  |  |  |  | Side |  |  |  |  | FR |  | 13
2012-07-11 | [8 empty] | FR |  |  |  | 10 | [20 empty] | CB | [5 empty] | 4 | [17 empty] | PLF | [5 empty] | 5 | [11 empty] | FP |  |  |  | 4 |  |  |  | Demo |  |  |  |  | 20 | FL | [5 empty] | 6 | [17 empty] | M |  |  |  | 8 | M |  |  |  |  | Side |  |  |  |  | R |  | 13
2012-07-12 | [8 empty] | FR |  |  |  | 10 | [20 empty] | CB | [5 empty] | 4 | [17 empty] | ELF | [5 empty] | 5 | [11 empty] | FP |  |  |  | 4 |  |  |  | Demo |  |  |  |  | 20 | FL | [5 empty] | 6 | [17 empty] | M |  |  |  | 8 | M |  |  |  |  | Side |  |  |  |  | R |  | 13
2012-07-13 | [8 empty] | FR |  |  |  | 10 | [20 empty] | CB | [5 empty] | 4 | [17 empty] | FP | [5 empty] | 5 | [11 empty] | FC |  |  |  | 7 |  |  |  | Demo |  |  |  |  | 20 | FL | [5 empty] | 6 | [17 empty] | M |  |  |  | 8 | M |  |  |  |  | Side |  |  |  |  | R |  | 13
2012-07-14
2012-07-15
2012-07-16 | [8 empty] | FR |  |  |  | 10 | [20 empty] | CT | [5 empty] | 4 | [17 empty] | FP | [5 empty] | 7 | [25 empty] | FL | [5 empty] | 6 | [17 empty] | M |  |  |  | 8 | IP |  |  |  |  | ELR |  |  |  |  | Demo |  | 4
2012-07-17 | [8 empty] | FR |  |  |  | 10 | [20 empty] | CT | [5 empty] | 4 | [17 empty] | FC | [5 empty] | 7 | [25 empty] | ELF | [5 empty] | 6 | [17 empty] | M |  |  |  | 8 | IP |  |  |  | 5 | ELR |  |  |  |  | D |  | 4
2012-07-18 | [8 empty] | FR |  |  |  | 10 | [20 empty] | PLF | [5 empty] | 4 | [49 empty] | T | [5 empty] | 6 | [17 empty] | M |  |  |  | 8 | FL |  |  |  | 5 | ELR |  |  |  |  | M |  | 4
2012-07-19 | [8 empty] | FR |  |  |  | 10 | [20 empty] | PLF | [55 empty] | T | [5 empty] | 6 | [17 empty] | M |  |  |  | 8 | FL |  |  |  | 5 | ELR |  |  |  |  | M |  | 4
2012-07-20 | [8 empty] | FR |  |  |  | 10 | [20 empty] | PLF | [55 empty] | FP | [5 empty] | 6 | [17 empty] | M |  |  |  | 8 | FL |  |  |  | 5 | ELR |  |  |  |  | IP |  | 4
2012-07-21
2012-07-22
2012-07-23 | [8 empty] | ELR |  |  |  | 10 | [20 empty] | ELF | [5 empty] | 4 | [73 empty] | IP |  |  |  | 8 | T |  |  |  | 3 | PLR |  |  |  |  | IP |  | 4
2012-07-24 | [8 empty] | ELR |  |  |  | 10 | [20 empty] | ELF | [5 empty] | 4 | [73 empty] | IP |  |  |  | 8 | T |  |  |  | 3 | PLR |  |  |  |  | FP |  | 4
2012-07-25 | [8 empty] | ELR |  |  |  | 10 | [20 empty] | FP | [5 empty] | 7 | [73 empty] | FL |  |  |  | 5 | T |  |  |  | 3 | PLR |  |  |  |  | FC |  | 4
2012-07-26 | [8 empty] | ELR |  |  |  | 10 | [20 empty] | FP | [5 empty] | 7 | [73 empty] | FL |  |  |  | 5 | T |  |  |  | 3 | I
2012-07-27 | [8 empty] | ELR |  |  |  | 10 | [20 empty] | FC | [5 empty] | 7 | [73 empty] | FL |  |  |  | 5 | T |  |  |  | 3 | I
2012-07-28
2012-07-29
2012-07-30 |  | MAS |  |  | 0 |  |  | 12 | FR |  | FR |  | 10 | MAS |  |  | MAS |  |  | 12 | [13 empty] | HOLD |  |  | HOLD | [20 empty] | FP |  |  | FP |  |  | 4 | [19 empty] | Site |  |  | Site | [26 empty] | FL |  | FL |  | 8 | M |  | M |  | 10 | HOLD |  | FR |  | 6 |  |  |  | FR |  | FR |  | 2 | MAS |  |  | MAS |  |  | 12 | ELR |  |  | ELR |  | 2
2012-07-31 |  | MAS |  |  | 0 |  |  | 12 | FR |  | FR |  | 10 | MAS |  |  | MAS |  |  | 12 | [13 empty] | HOLD |  |  | HOLD | [20 empty] | FP |  |  | FP |  |  | 4 | [19 empty] | Site |  |  | Site | [26 empty] | FL |  | FL |  | 8 | M |  | M |  | 10 | HOLD |  | FR |  | 6 |  |  |  | FR |  | FR |  | 10 | MAS |  |  | MAS |  |  | 12 | ELR |  |  | ELR |  | 2
2012-08-01 |  | MAS |  |  | 0 |  |  | 12 | FR | SF | FR |  | 10 | MAS |  |  | MAS |  |  | 12 | [13 empty] | HOLD |  |  | HOLD | [20 empty] | FP |  |  | FP |  |  | 4 | [19 empty] | Site |  |  | Site | [26 empty] | FL |  | FL |  | 8 | M |  | M |  | 10 | HOLD |  | HOLD |  | 0 |  |  |  | FR |  | FR |  | 10 | MAS |  |  | MAS |  |  | 12 | FR |  |  | FR |  | 10
2012-08-02 |  | MAS |  |  | MAS |  |  | 12 | FR | SF | FR | SF | 10 | MAS |  |  | MAS |  |  | 12 | [13 empty] | HOLD |  |  | HOLD | [20 empty] | FP |  |  | FP |  |  | 4 | [19 empty] | Site |  |  | Site | [26 empty] | FL |  | FL |  | 8 | M |  | M |  | 10 | HR |  | FR |  | 0 |  |  |  | FR |  | FR |  | 10 | MAS |  |  | MAS |  |  | 12 | FR |  |  | FR |  | 10
2012-08-03 |  | MAS |  |  | MAS |  |  | 12 | FR | Side | FR | Side | 10 | MAS |  |  | MAS |  |  | 12 | [13 empty] | HOLD |  |  | HOLD | [20 empty] | FP |  |  | FP |  |  | 4 | [19 empty] | Site |  |  | Site | [26 empty] | FL |  | FL |  | 8 | M |  | M |  | 10 | HR |  | HR |  | 0 |  |  |  | FR | R | FR | R | 10 | MAS |  |  | MAS |  |  | 12 | FR |  |  | 0 |  | 10
2012-08-04
2012-08-05
2012-08-06 |  | MAS |  |  | MAS |  |  | 12 | Side | ELR | ELR | PLR | 10 | FR |  |  | FR |  |  | 12 | Site |  |  | Site | [9 empty] | HOLD |  |  | HOLD | [46 empty] | MAS |  |  | Site |  | 12 | [24 empty] | FL |  | 0 |  | 8 | FL |  | FL |  | 8 | I |  | 0 |  | 10 |  |  |  | FR | R | FR | R | 10 | FR |  |  | FR |  |  | 12 | I |  |  | I |  | 10
2012-08-07 |  | MAS |  |  | MAS |  |  | 12 | Side | ELR | Side | ELR | 10 | FR |  |  | FR |  |  | 12 | Site |  |  | Site | [9 empty] | HOLD |  |  | HOLD | [46 empty] | MAS |  |  | Site |  | 12 | [24 empty] | FL |  | FL |  | 8 | FL |  | FL |  | 8 | I |  | 0 |  | 10 |  |  |  | FR | EWD | FR | EWD | 10 | FR |  |  | FR |  |  | 12 | I |  |  | I |  | 10
2012-08-08 |  | MAS |  |  | MAS |  |  | 12 | Side | ELR | ELR | PLR | 4 | FR |  |  | FR |  |  | 12 | Site |  |  | Site | [9 empty] | HOLD |  |  | HOLD | [46 empty] | MAS |  |  | Site |  | 12 | [24 empty] | FL |  | FL |  | 8 | FL |  | FL |  | 8 | D |  | 0 |  | 10 |  |  |  | FR | SF | 0 |  | 10 | FR |  |  | FR |  |  | 12 | D |  |  | D |  | 10
2012-08-09 |  | MAS | [5 empty] | 12 | PLR | HR | PLR | HR | 4 | FR |  |  | FR |  |  | 12 | Site |  |  | Site | [9 empty] | HOLD |  |  | HOLD | [46 empty] | MAS |  |  | Site |  | 12 | [24 empty] | FL |  | FL |  | 8 | FL |  | FL |  | 8 | D |  | 0 |  | 10 |  |  |  | FR | SF | FR | EWD | 10 | FR |  |  | FR |  |  | 12 | D |  |  | D |  | 10
2012-08-10 |  | MAS | [5 empty] | 12 | PLR | HR | PLR | HR | 4 | FR |  |  | FR |  |  | 12 | Site |  |  | Site | [9 empty] | HOLD |  |  | HOLD | [46 empty] | MAS |  |  | Site |  | 12 | [24 empty] | FL |  | FL |  | 8 | FL |  | FL |  | 8 | D |  | 0 |  | 10 |  |  |  | FR | Side | FR | Side | 10 | FR |  |  | FR |  |  | 12 | D |  |  | D |  | 10
2012-08-11
2012-08-12
2012-08-13 |  | FR | [5 empty] | 12 | I |  | 0 |  | 10 | FR | R |  | 0 |  |  | 12 | MAS |  |  | 0 |  | 12 | [7 empty] | CB |  |  | HOLD |  |  | 4 | [43 empty] | MAS |  |  | 0 |  | 12 | [24 empty] | T |  | 0 |  | 8 | PLF |  | 0 |  | 2 | M |  | 0 |  | 10 |  |  |  | Side | ELR | Side | ELR | 10 | FR | R |  | 0 |  |  | 12 | D |  |  | 0 |  | 10
2012-08-14 |  | FR | [5 empty] | 12 | I |  | 0 |  | 10 | FR | EWD |  | 0 |  |  | 12 | MAS |  |  | 0 |  | 12 | [7 empty] | CT |  |  | HOLD |  |  | 4 | [43 empty] | MAS |  |  | 0 |  | 12 | [24 empty] | T |  | 0 |  | 8 | PLF |  | 0 |  | 2 | M |  | 0 |  | 10 |  |  |  | Side | ELR | Side | ELR | 10 | FR | EWD |  | 0 |  |  | 12 | D |  |  | 0 |  | 10
2012-08-15 |  | FR | [5 empty] | 12 | D |  | 0 |  | 10 | FR | SF |  | 0 |  |  | 12 | MAS |  |  | 0 |  | 12 | [7 empty] | CT |  |  | HOLD |  |  | 4 | [43 empty] | MAS |  |  | 0 |  | 12 | [24 empty] | T |  | 0 |  | 8 | PLF | ELF | 0 |  | 2 | M |  | 0 |  | 10 |  |  |  | ELR | PLR | ELR | PLR | 4 | FR | SF |  | 0 |  |  | 12 | D |  |  | 0 |  | 10
2012-08-16 |  | FR | [5 empty] | 12 | D |  | 0 |  | 10 | FR | SF |  | 0 |  |  | 12 | MAS |  |  | 0 |  | 12 | [7 empty] | SF |  |  | HOLD |  |  | 4 | [43 empty] | MAS |  |  | 0 |  | 12 | [24 empty] | T |  | FL |  | 8 | ELF |  | 0 |  | 2 | M |  | 0 |  | 10 |  |  |  | PLR | HR | PLR | HR | 2 | FR | SF |  | 0 |  |  | 12 | IP |  |  | 0 |  | 10
2012-08-17 |  | FR | R |  |  |  |  | 12 | D |  | 0 |  | 10 | FR | Side |  | 0 |  |  | 12 | MAS |  |  | 0 |  | 12 | [7 empty] | SF |  |  | HOLD |  |  | 4 | [43 empty] | MAS |  |  | 0 |  | 12 | [24 empty] | T |  | FL |  | 2 | ELF |  | 0 |  | 2 | M |  | 0 |  | 10 |  |  |  | PLR | HR | PLR | HR | 2 | FR | Side |  | 0 |  |  | 12 | IP |  |  | 0 |  | 10
2012-08-18
2012-08-19
2012-08-20 |  | FR | R |  |  |  |  | 12 | M |  | 0 |  | 8 | Side | ELR |  | 0 |  |  | 12 | FR |  |  | 0 |  | 12 | [7 empty] | FP |  |  | HOLD |  |  | 4 | [43 empty] | FR |  |  | 0 |  | 12 | [24 empty] | PLF |  |  |  | 2 | FP |  | 0 |  | 4 | M |  | D |  | 10 |  |  |  | I |  | I |  | 10 | Side | ELR |  | 0 |  |  | 12 | FL |  |  | 0 |  | 8
2012-08-21 |  | FR | EWD |  |  |  |  | 12 | M |  | 0 |  | 8 | Side | ELR |  | 0 |  |  | 12 | FR |  |  | 0 |  | 12 | [7 empty] | FP |  |  | HOLD |  |  | 4 | [43 empty] | FR |  |  | 0 |  | 12 | [24 empty] | PLF |  |  |  | 2 | FP |  | D |  | 4 | M |  | D |  | 10 |  |  |  | I |  | I |  | 10 | Side | ELR |  | 0 |  |  | 12 | FL |  |  | 0 |  | 8
2012-08-22 |  | FR | SF |  |  |  |  | 12 | M |  | 0 |  | 8 | ELR | PLR |  |  |  |  | 4 | FR |  |  | 0 |  | 12 | [7 empty] | FC |  |  | HOLD |  |  | 4 | [43 empty] | FR |  |  | MAS |  | 12 | [24 empty] | PLF | ELF |  |  | 2 | FP |  | D | FL | 4 | M |  | D | FL | 10 |  |  |  | D |  | D |  | 10 | ELR | PLR |  | 0 |  |  | 4 | FL |  |  | 0 |  | 8
2012-08-23 |  | FR | SF |  |  |  |  | 12 | M |  | 0 |  | 8 | PLR | HR |  |  |  |  | 4 | MAS |  |  | 0 |  | 12 | [7 empty] | FC |  |  | HOLD |  |  | 8 | [43 empty] | FR |  |  | MAS |  | 12 | [24 empty] | ELF |  |  |  | 2 | FC |  | FL |  | 8 | M |  | D |  | 10 |  |  |  | D |  | D |  | 10 | PLR | HR |  | 0 |  |  | 4 | T |  |  | 0 |  | 8
2012-08-24 |  | FR | Side |  |  |  |  | 12 | M |  | 0 |  | 8 | PLR | HR |  |  |  |  | 4 | MAS |  |  | 0 |  | 12 | [57 empty] | FR | R |  |  |  | 12 | [24 empty] | ELF |  |  |  | 2 | FC |  |  |  | 8 | M |  |  |  | 10 |  |  |  | D |  | D |  | 10 | PLR | HR |  | 0 |  |  | 4 | T |  |  | 0 |  | 8
2012-08-25
2012-08-26
2012-08-27 |  | Side | ELR |  |  |  |  | 12 | M |  |  |  | 8 | I | [5 empty] | 10 | FR |  |  |  |  | 12 | [57 empty] | FR | R |  |  |  | 12 | [24 empty] | FP |  |  |  | 4 | [5 empty] | IP |  |  |  | 10 |  |  |  | M |  |  |  | 10 | I |  |  | 0 |  |  | 10 | PLF |  |  |  |  | 2
2012-08-28 |  | Side | ELR |  |  |  |  | 12 | M |  |  |  | 10 | I | [5 empty] | 10 | FR |  |  |  |  | 12 | [57 empty] | FR | EWD |  |  |  | 12 | [24 empty] | FP |  |  |  | 4 | [5 empty] | IP |  |  |  | 10 |  |  |  | M |  |  |  | 10 | I |  |  | 0 |  |  | 10 | PLF |  |  |  |  | 2
2012-08-29 |  | ELR | PLR |  |  |  |  | 12 | M |  |  |  | 10 | D | [5 empty] | 10 | FR |  |  |  |  | 12 | [57 empty] | FR | SF |  |  |  | 12 | [24 empty] | FP |  |  |  | 4 | [5 empty] | FL |  |  |  | 8 |  |  |  | M |  |  |  | 10 | D |  |  | 0 |  |  | 10 | PLF | ELF |  |  |  | 2
2012-08-30 |  | PLR | HR |  |  |  |  | 12 | M |  |  |  | 10 | D | [5 empty] | 10 | FR |  |  |  |  | 12 | [57 empty] | FR | SF |  |  |  | 12 | [24 empty] | FC |  |  |  | 8 | [5 empty] | FL |  |  |  | 8 |  |  |  | M |  |  |  | 10 | D |  |  | 0 |  |  | 10 | ELF |  |  |  |  | 2
2012-08-31 | [8 empty] | HOLD |  | HOLD |  | 10
2012-09-01
2012-09-02
2012-09-03 | [8 empty] | HOLD |  | HOLD
2012-09-04 | [8 empty] | HOLD |  | HOLD
2012-09-05 | [8 empty] | HOLD |  | HOLD
2012-09-06 | [8 empty] | HOLD |  | HOLD
2012-09-07 | [8 empty] | HOLD |  | HOLD
2012-09-08
2012-09-09
2012-09-10 | [8 empty] | HOLD |  | HOLD
2012-09-11 | [8 empty] | HOLD |  | HOLD
2012-09-12 | [8 empty] | HOLD |  | HOLD
2012-09-13 | [8 empty] | HOLD |  | HOLD
2012-09-14 | [8 empty] | HOLD |  | HOLD
2012-09-15
2012-09-16
2012-09-17 |  | HOLD |  |  | HOLD |  |  |  | HOLD |  | HOLD |  |  | FR |  |  | FR |  |  | 12 | [63 empty] | D |  |  | D |  | 10 | [34 empty] | FL |  | FL | [5 empty] | FL |  | FL |  | 8 | FR |  |  | FR |  |  | 12 | D |  |  | D |  | 0
2012-09-18 |  | HOLD |  |  | HOLD |  |  |  | HOLD |  | HOLD |  |  | FR |  |  | FR |  |  | 12 | [63 empty] | D |  |  | D |  | 10 | [34 empty] | FL |  | FL | [5 empty] | FL |  | FL |  | 8 | FR |  |  | FR |  |  | 12 | D |  |  | D |  | 0
2012-09-19 |  | HOLD |  |  | HOLD |  |  |  | HOLD |  | HOLD |  |  | FR |  |  | FR |  |  | 12 | [63 empty] | D |  |  | D |  | 10 | [34 empty] | FL |  | FL | [5 empty] | FL |  | FL |  | 8 | FR |  |  | FR |  |  | 12 | D |  |  | D |  | 0
2012-09-20 |  | HOLD |  |  | HOLD |  |  |  | HOLD |  | HOLD |  |  | FR |  |  | FR |  |  | 12 | [63 empty] | D |  |  | D |  | 10 | [34 empty] | FL | ELF | T | ELF |  |  |  |  | FL |  | FL |  | 8 | FR |  |  | FR |  |  | 12 | D |  |  | D |  | 0
2012-09-21 |  | HOLD |  |  | HOLD |  |  |  | HOLD |  | HOLD |  |  | FR |  |  | FR | R |  | 12 | [63 empty] | D |  |  | D | M | 10 | [34 empty] | FL | ELF | T | [5 empty] | FL |  | FL |  | 8 | FR | R |  | FR | R |  | 12 | D |  |  | D |  | 0
2012-09-22
2012-09-23
2012-09-24 |  | HOLD |  |  | HOLD |  |  |  | HOLD |  | HOLD |  |  | FR | R |  | FR | R | [65 empty] | M |  |  | M |  | 10 | [34 empty] | FL |  | 0 | [5 empty] | FL |  | FL |  | 8 | FR | R |  | FR | R |  | 12 | D | PLF |  | D |  | 8
2012-09-25 |  | HOLD |  |  | HOLD |  |  |  | HOLD |  | HOLD |  |  | FR | EWD |  | FR | R | [65 empty] | M |  |  | M |  | 10 | [34 empty] | FL |  | 0 | [5 empty] | FL |  | FL |  | 8 | FR | EWD |  | FR | R |  | 12 | FL |  |  | D |  | 8
2012-09-26 |  | HOLD |  |  | HOLD |  |  |  | HOLD |  | HOLD |  |  | FR | SF |  | ELR | PLR | [65 empty] | M |  |  | M |  | 10 | [34 empty] | CB | HF | 0 | [5 empty] | CB | HF | T | ELF | 8 | FR | SF |  | ELR | PLR |  | 12 | FL | T | ELF | D |  | 8
2012-09-27 |  | HOLD |  |  | HOLD |  |  |  | HOLD |  | HOLD |  |  | FR | SF |  | ELR | PLR | [65 empty] | M |  |  | M |  | 10 | [34 empty] | T |  | 0 | [5 empty] | T | ELF | T | ELF | 8 | FR | SF |  | ELR | PLR |  | 12 | T |  |  | D |  | 8
2012-09-28 |  | HOLD |  |  | HOLD |  |  |  | FR | Side | FR | Side |  | FR | SF |  | ELR | PLR | [65 empty] | M |  |  | M |  | 10 | [34 empty] | T |  | 0 | [5 empty] | T | ELF | T | ELF | 8 | FR | SF |  | ELR | PLR |  | 12 | T | FP |  | D |  | 8
2012-09-29
2012-09-30
2012-10-01 |  | HOLD |  |  | HOLD |  |  |  | I |  | FR |  |  | Side | ELR |  | I |  |  | 10 | [63 empty] | M |  |  | M |  | 10 | [34 empty] | T | PLF | 0 | [5 empty] | T | PLF | CB |  | 8 | Side | ELR |  | I |  |  | 10 | FL |  |  | 0
2012-10-02 |  | HOLD |  |  | HOLD |  |  |  | I |  | 0 |  |  | Side | ELF |  | I |  |  | 10 | [63 empty] | M |  |  | M |  | 10 | [34 empty] | T | PLF | 0 | [5 empty] | T | PLF | T | PLF | 8 | Side | ELF |  | I |  |  | 10 | FL |  |  | 0
2012-10-03 |  | HOLD |  |  | HOLD |  |  |  | D |  | 0 |  |  | Side | ELR | PLR | D |  |  | 10 | [63 empty] | M |  |  | M |  | 10 | [34 empty] | T |  | CB | [5 empty] | T |  | T |  | 8 | Side | ELR | PLF | D |  |  | 10 | HOLD
2012-10-04 |  | HOLD |  |  | HOLD |  |  |  | D |  | 0 |  |  | Side | PLR | HR | D |  |  | 10 | [63 empty] | M |  |  | M |  | 10 | [34 empty] | T |  | CT | [5 empty] | T |  | T |  | 8 | Side | PLR | HR | D |  |  | 10 | HOLD
2012-10-05 |  | HOLD |  |  | HOLD |  |  |  | D |  | 0 |  |  | Side | PLR | HR | D |  |  | 10 | [63 empty] | M |  |  | M |  | 10 | [34 empty] | T |  | CT | [5 empty] | T |  | T |  | 8 | Side | PLR | HR | D |  |  | 10 | HOLD
2012-10-06
2012-10-07
2012-10-08 |  | HOLD |  |  | HOLD |  |  |  | FR |  | RWK |  |  | I | GTR |  | D | Side |  | 10 | FR |  |  | MAS |  |  | MAS |  |  | MAS | [53 empty] | IP |  |  | 0 |  | 10 | [34 empty] | FP |  | PLF |  | 8 |  |  |  | FP |  | FP |  | 8 | I | GTR |  | D | Side |  | 10 | HOLD | [9 empty] | Demo |  |  | Demo |  |  | 10 | Demo |  | Demo
2012-10-09 |  | HOLD |  |  | HOLD |  |  |  | FR |  | RWK |  |  | D |  |  | D | Side |  | 10 | FR |  |  | MAS |  |  | MAS |  |  | MAS | [53 empty] | IP |  |  | IP |  | 10 | [34 empty] | FP |  | FP |  | 0 |  |  |  | FP |  | 0 |  | 8 | D |  |  | D | Side |  | 10 | HOLD | [9 empty] | Demo |  |  | Demo |  |  | 10 | Demo |  | Demo
2012-10-10 |  | HOLD |  |  | HOLD |  |  |  | FR |  | EP | FR | 8 | D |  |  | M | Side |  | 10 | FR |  |  | FR |  |  | MAS |  |  | MAS | [53 empty] | FL |  |  | IP |  | 8 | [34 empty] | FP |  | FP |  | 8 |  |  |  | FP |  | FP |  | 8 | D |  |  | M | Side |  | 10 | HOLD | [9 empty] | Demo |  |  | Demo |  |  | 10 | Demo |  | FR | R
2012-10-11 |  | HOLD |  |  | HOLD |  |  |  | FR |  | EP | FR | 8 | D |  |  | M | Side |  | 10 | FR |  |  | FR |  |  | MAS |  |  | MAS | [53 empty] | FL |  |  | IP |  | 8 | [34 empty] | FC |  | FP |  | 8 |  |  |  | FC |  | FC |  | 8 | D |  |  | M | Side |  | 10 | HOLD | [9 empty] | Demo |  |  | Demo |  |  | 10 | Demo |  | FR | R
2012-10-12 |  | HOLD |  |  | HOLD |  |  |  | FR |  | FR |  | 8 | D |  |  | M | Side |  | 10 | FR | R |  | FR |  |  | MAS |  |  | MAS | [53 empty] | FL |  |  | FL |  | 8 | [34 empty] | FC |  | FC |  | 8 |  |  |  | FC |  | FC |  | 8 | D |  |  | M | Side |  | 10 | HOLD | [9 empty] | Demo |  |  | HOLD |  |  | 10 | Demo |  | FR | R
2012-10-13
2012-10-14
2012-10-15 |  | HOLD |  |  | HOLD |  |  |  | ELR |  | Side | SF | 9 | M |  |  | M | Side |  | 10 | FR | R |  | FR |  |  | FR |  |  | FR | [53 empty] | FL |  |  | FL |  | 8 | [47 empty] | M |  |  | M | Side |  | 10 | HOLD | [5 empty] | Demo | Demo |  | 8 | FR |  |  | HOLD |  |  | 10 | FR |  | ELR
2012-10-16 |  | HOLD |  |  | HOLD |  |  |  | ELR |  | 0 |  | 9 | M |  |  | M | Side |  | 10 | FR | EWD |  | FR |  |  | FR |  |  | FR | [53 empty] | FL |  |  | FL |  | 8 | [47 empty] | M |  |  | M | Side |  | 10 | HOLD | [5 empty] | FR | FR | D | 8 | FR |  |  | HOLD |  |  | 10 | FR |  | PLR
2012-10-17 |  | HOLD |  |  | HOLD |  |  |  | FR |  | 0 |  | 8 | M |  |  | M | Side |  | 10 | FR | SF |  | FR |  |  | FR |  |  | FR | [53 empty] | T | CB |  | FL |  | 8 | [47 empty] | M |  |  | M | Side |  | 10 | HOLD | [5 empty] | ELR | D |  | 8 | FR |  |  | HOLD |  |  | 10 | FR |  | HOLD
2012-10-18 |  | HOLD |  |  | HOLD |  |  |  | FR |  | FR | ELR | 8 | M |  |  | M | Side |  | 10 | FR | SF |  | FR |  |  | FR |  |  | FR | [53 empty] | T | ELF |  | FL |  | 8 | [47 empty] | M |  |  | M | Side |  | 10 | HOLD | [5 empty] | I | D |  | 8 | FR |  |  | HOLD |  |  | 10 | FR
2012-10-19 |  | HOLD |  |  | HOLD |  |  |  | FR |  | FR |  | 8 | M |  |  | M | Side |  | 10 | FR | SF |  | FR |  |  | FR | R |  | FR | [53 empty] | T | ELF |  | FL |  | 8 | [47 empty] | M |  |  | M |  |  | 10 | HOLD | [5 empty] | I | M |  | 8 | FR |  |  | HOLD |  |  | 10 | FR
2012-10-20
2012-10-21
2012-10-22 |  | HOLD |  |  | HOLD |  |  |  | FR |  | FR |  | 8 | M |  |  | M |  |  | 10 | Side | ELR |  | FR |  |  | FR | R |  | FR | [53 empty] | T | PLF |  | T | CB | 8 | [47 empty] | M |  |  | M |  |  | 10 | FL |  |  | FL |  | 4 | D | M |  | 8 | FR |  |  | HOLD |  |  | 10 | R | FR | I
2012-10-23 |  | HOLD |  |  | HOLD |  |  |  | FR |  | FR |  | 8 | M |  |  | IP |  |  | 10 | Side | ELR |  | FR |  |  | FR | EWD |  | FR | [53 empty] | T | PLF |  | T |  | 8 | [47 empty] | M |  |  | IP |  |  | 10 | T | PLF |  | T | PLF | 4 | D | M |  | 8 | FR |  |  | HOLD |  |  | 10 | R | FR | D
2012-10-24 |  | HOLD |  |  | HOLD |  |  |  | I |  | FR |  | 10 | M |  |  | IP |  |  | 10 | Side | ELR |  | FR |  |  | FR | SF |  | FR | [53 empty] | T | HF |  | T | PLF | 8 | [47 empty] | M |  |  | IP |  |  | 10 | T | PLF |  | T | PLF | 4 | D | M |  | 8 | FR |  |  | HOLD |  |  | 10 | R | FR | D
2012-10-25 |  | HOLD |  |  | HOLD |  |  |  | I |  | I |  | 10 | M |  |  | FL |  |  | 10 | Side | PLR | HR | FR |  |  | FR | SF |  | FR | [53 empty] | T |  |  | T | PLF | 8 | [47 empty] | M |  |  | FL |  |  | 10 | T | ELF |  | T |  | 4 | D | IP |  | 8 | FR |  |  | HOLD |  |  | 10 | R | FR | D
2012-10-26 |  | HOLD |  |  | HOLD |  |  |  | I |  | I | D | 10 | M |  |  | FL |  |  | 10 | Side | PLR | HR | FR |  |  | FR | SF |  | FR | [53 empty] | T |  |  | T | FP | 8 | [47 empty] | M |  |  | FL |  |  | 10 | T | ELF |  | T |  | 4 | D | FL |  | 8 | FR |  |  | HOLD |  |  | 10 | R | FR | D
2012-10-27
2012-10-28
2012-10-29 |  | HOLD |  |  | HOLD |  |  |  | D |  | D |  | 10 | IP |  |  | FL |  |  | 10 | I | GTR |  | FR |  |  | Side | ELR |  | FR | [53 empty] | FP |  |  | FP |  | 8 | [47 empty] | IP |  |  | FL |  |  | 10 | Side |  |  | T |  | 4 | IP | FL |  | 8 | Side | ELR |  |  |  |  | 10 | ELR | PLR | D
2012-10-30 |  | HOLD |  |  | HOLD |  |  |  | D |  | D |  | 10 | IP |  |  | FL |  |  | 10 | I |  |  | FR |  |  | Side | ELR |  | FR | [53 empty] | FP |  |  | FP |  | 8 | [47 empty] | IP |  |  | FL |  |  | 10 | Side |  |  | T |  | 4 | FL | T |  | 8 | Side | ELR |  |  |  |  | 10 | I |  | D
2012-10-31 |  | HOLD |  |  | HOLD |  |  |  | D |  | D |  | 10 | FL |  |  | FL |  |  | 10 | D |  |  | FR | R |  | Side | ELR | PLR | FR | [53 empty] | FP |  |  | FP |  | 8 | [47 empty] | FL |  |  | FL |  |  | 10 | Side |  |  |  |  | 4 | FL | T |  | 8 | Side | ELR | PLR |  |  |  | 10 | D |  | M
2012-11-01 |  | HOLD |  |  | HOLD |  |  |  | D |  | D |  | 10 | FL |  |  | 0 |  |  | 10 | D |  |  |  | R |  | Side | PLR | HR | FR | R | [52 empty] | FC |  |  | FC |  | 8 | [47 empty] | FL |  |  | 0 |  |  | 10 | FP |  |  |  |  | 4 | T | T |  | 8 | SF | PLR |  |  |  |  | 10 | D |  | M
2012-11-02 |  | HOLD |  |  | HOLD |  |  |  | D |  | D |  | 10 | FL |  |  | 0 |  |  | 10 | D |  |  |  | R |  | Side | PLR | HR | 0 | [53 empty] | FC |  |  | FC |  | 8 | [47 empty] | FL |  |  | 0 |  |  | 10 | FP |  |  |  |  | 4 | T | T |  | 8 | SF | PLR |  |  |  |  | 10 | D |  | M
2012-11-03
2012-11-04
2012-11-05 | [8 empty] | D |  | D |  | 10 | FL |  |  | FL |  |  | 10 | D |  |  | ELR | PLR |  | I | GTR |  | SF | ELR | PLR | [104 empty] | FL |  |  | FL |  |  | 10 | [6 empty] | FP | FP |  |  | I | [5 empty] | 10 | D |  | M
2012-11-06 | [8 empty] | D |  | D | SF | 10 | FL |  |  | FL |  |  | 10 | D |  |  | ELR | PLR |  | I |  |  | SF | ELR | PLR | [104 empty] | FL |  |  | FL |  |  | 10 | [6 empty] | FP | FP |  |  | I | [5 empty] | 10 | D |  | M
2012-11-07 | [8 empty] | D |  | D |  | 10 | T | CB |  | FL |  |  | 10 | M |  |  | ELR | PLR |  | D |  |  | SF | ELR | PLR | [104 empty] | T | CB |  | FL | T |  | 10 | [6 empty] | FC | FC |  |  | D | [5 empty] | 10 | M |  | M
2012-11-08 |  | MAS |  |  | MAS |  |  |  | M |  | M |  | 10 | T | ELF |  | FL | CB | T | 10 | M |  |  | ELR | PLR |  | D |  |  | SF | ELR | PLR | [104 empty] | T | ELF |  | FL | CB | T | 10 | [10 empty] | D | [5 empty] | 10 | M |  | M
2012-11-09 |  | MAS |  |  | MAS |  |  |  | M |  | M | SF | 10 | T | ELF |  | FL | CB | T | 10 | M |  |  | PLR |  |  | D |  |  | SF | HR | [105 empty] | T | ELF |  | FL | CB | T | 10 | [10 empty] | D | [5 empty] | 10 | M |  | M
2012-11-10
2012-11-11
2012-11-12 |  | FR |  |  | FR |  |  |  | M |  | M |  | 10 | T | PLF |  | T |  |  | 10 | M |  |  | D |  |  | D |  |  | D | [106 empty] | T | PLF |  | T | 0 |  | 10 | [10 empty] | D | [5 empty] | 10 | M |  | M
2012-11-13 |  | FR |  |  | FR |  |  |  | M |  | M |  | 10 | T | PLF |  | T |  |  | 10 | M |  |  | D |  |  | D |  |  | D | [106 empty] | T | PLF |  | T | 0 |  | 10 | [10 empty] | D | [5 empty] | 10 | M |  | M
2012-11-14 |  | FR |  |  | FR |  |  |  | M |  | M |  | 10 | T | HF |  | T |  |  | 10 | M |  |  | D |  |  | M |  |  | D | [106 empty] | T | HF |  | T | 0 |  | 10 | [10 empty] | M | [5 empty] | 10 | M |  | IP
2012-11-15 |  | FR |  |  | FR |  |  |  | M |  | M |  | 10 | T |  |  | T | T |  | 10 | M |  |  | M | D |  | M |  |  | M | D | [105 empty] | T |  |  | T |  |  | 10 | [10 empty] | M | [5 empty] | 10 | M |  | IP
2012-11-16 |  | FR |  |  | FR |  |  |  | M |  | M |  | 10 | T |  |  | T | T |  | 10 | M |  |  | M |  |  | M |  |  | M | [106 empty] | T |  |  | T |  |  | 10 | [10 empty] | M | [5 empty] | 10 | M
2012-11-17
2012-11-18
2012-11-19 |  | FR |  |  | FR |  |  | MEN | M |  | M |  | 10 | T |  |  | T |  |  | 8 | M |  |  | M |  | MEN | M |  |  | D |  |  | MEN | [103 empty] | T |  |  | T |  |  | 8 | [13 empty] | HOLD |  |  |  | IP |  | FL |  |  | SS | [6 empty] | MAS |  |  | MAS |  |  | CDS
2012-11-20 |  | FR |  |  | FR |  |  | MEN | M |  | M |  | 10 | T |  |  | T |  |  | 8 | M |  |  | M |  | MEN | M |  |  | D |  |  | MEN | [103 empty] | T |  |  | T |  |  | 8 | [13 empty] | HOLD |  |  |  | IP |  | FL |  |  | SS | [6 empty] | MAS |  |  | MAS |  |  | CDS
2012-11-21 |  | FR |  |  | FR |  |  | MEN | M |  | M |  | 10 | T |  |  | T |  |  | 8 | M |  |  | M |  | MEN | M |  |  | D | M |  | MEN | [103 empty] | T |  |  | T |  |  | 8 | [13 empty] | HOLD |  |  |  | FL |  | 0 |  |  | SS | [6 empty] | MAS |  |  | MAS |  |  | CDS
2012-11-22 |  | 0 |  |  | 0 |  |  | MEN | 0 |  | M |  | 0 |  |  |  | 0 | [9 empty] | HOLD |  |  | 0 |  |  | MEN | [103 empty] | HOLD |  |  | HOLD |  |  | 0 | [13 empty] | HOLD | [5 empty] | 0 | [12 empty] | 0
2012-11-23 |  | 0 |  |  | FR | R |  | MEN | 0 |  | M |  | 0 |  |  |  | 0 | [9 empty] | HOLD |  |  | 0 |  |  | MEN | [123 empty] | HOLD | [5 empty] | 0 | [12 empty] | 0
2012-11-24
2012-11-25
2012-11-26 |  | FR | R |  | FR | R |  | MEN | M |  | M |  | 5 | MAS |  |  | PLF | ELF |  | 8 | M |  |  |  |  | MEN | M |  |  | 0 |  |  | MEN | [103 empty] | MAS |  |  | PLF | ELF |  | 8 | [13 empty] | HOLD |  |  |  | FL |  | T |  |  | SS | [6 empty] | MAS |  |  | MAS |  |  | CDS
2012-11-27 |  | FR | R |  | FR | R |  | MEN | M |  | M |  | 5 | MAS |  |  | PLF | ELF |  | 8 | M |  |  |  |  | MEN | M |  |  | 0 |  |  | MEN | [103 empty] | MAS |  |  | PLF | ELF |  | 8 | [13 empty] | HOLD |  |  |  | FL |  | T |  |  | SS | [6 empty] | MAS |  |  | MAS |  |  | CDS
2012-11-28 |  | FR | EWD |  | FR |  |  | MEN | M |  | M |  | 5 | MAS |  |  | PLF | ELF | MAS | 8 | M |  |  |  |  | MEN | M |  |  | 0 |  |  | MEN | [103 empty] | MAS |  |  | MAS | PLF | ELF | 8 | [13 empty] | HOLD |  |  |  | CB | HF | T | CB |  | SS | [6 empty] | MAS |  |  | MAS |  |  | CDS
2012-11-29 |  | FR | SF |  | FR | SF |  | MEN | IP |  | M | IP | 5 | MAS |  |  | MAS | FP |  | 8 | M |  |  | M |  | MEN | M |  |  | 0 |  |  | MEN | [103 empty] | MAS |  |  | MAS | FP |  | 8 | [13 empty] | HOLD |  |  |  | T | ELF | T | CB | FL | SS | [6 empty] | MAS |  |  | MAS |  |  | CDS
2012-11-30 |  | FR | SF |  | FR | SF |  | MEN | IP |  | IP |  | 13 | MAS |  |  | FC |  |  | 8 | M |  |  | M |  | MEN | M |  |  | 0 |  |  | MEN | [103 empty] | MAS |  |  | FC |  |  | 8 | [13 empty] | HOLD |  |  |  | T | ELF | T | ELF |  | SS | [6 empty] | MAS |  |  | MAS |  |  | CDS
2012-12-01
2012-12-02
2012-12-03 |  | Side | ELR |  | SF | Side |  | MEN | FL |  | FL |  | 0 | FR |  |  | FC |  |  | 8 | M |  |  | M |  | MEN | M |  |  | 0 |  |  | 0 | [103 empty] | FR |  |  | FC |  |  | 8 | [13 empty] | HOLD |  |  |  | T | PLF | T | ELF |  | SS | [6 empty] | MAS |  |  | MAS |  |  | CDS | Demo | 0 | 8
2012-12-04 |  | Side | ELR |  | SF | Side | ELR |  | FL |  | FL | T | 12 | FR |  |  | FC |  |  | 8 | M |  |  | M |  | MEN | M |  |  | 0 |  |  | 0 | [103 empty] | FR |  |  | FC |  |  | 8 | [13 empty] | HOLD |  |  |  | T | PLF | T | ELF |  | SS | [6 empty] | MAS |  |  | FR |  |  | MEN | D | Demo | 3
2012-12-05 |  | Side | ELR |  | FG | ELR |  |  | CB |  | T |  | 12 | FP | [6 empty] | IP |  |  | M |  | MEN | IP |  |  | 0 |  |  | 0 | [103 empty] | FP | [5 empty] | 8 | [13 empty] | HOLD |  |  |  | T |  | T | PLF |  | SS | [6 empty] | FR |  |  | FR |  |  | MEN | M | I | 3
2012-12-06 |  | Side | PLR | HR | Side | HR | ELR |  | T | ELF | T | CB | 12 | FP | [6 empty] | IP |  |  | M |  | MEN | IP |  |  | M |  |  | 0 | [103 empty] | FP | [5 empty] | 8 | [13 empty] | HOLD |  |  |  | T |  | T |  |  | SS | [6 empty] | FR |  |  | FR |  |  | MEN | M | D | 8
2012-12-07 |  | Side | PLR | HR | 0 |  |  |  | T | ELF | T |  | 0 | FP | [6 empty] | FL |  |  | 0 |  | MEN | FL |  |  | 0 |  |  | 0 | [103 empty] | FP | [5 empty] | 8 | [13 empty] | HOLD |  |  |  | T |  | T |  |  | SS | [6 empty] | FR | R |  | 0 |  |  | MEN | IP | D | 3
2012-12-08
2012-12-09
2012-12-10 |  | I | GTR |  | 0 |  |  | HD | T | PLF | T | PLF | 8 | FC | [6 empty] | FL |  |  | 0 |  | MEN | FL |  |  | 0 |  |  | 0 | [103 empty] | FC | [5 empty] | 8 | [13 empty] | HOLD |  |  |  | FP |  | FP |  |  | SS | [6 empty] | FR |  |  | 0 |  |  | MEN | D | 0
2012-12-11 |  | I | GTR |  | 0 |  |  | HD | T | PLF | T | PLF | 8 | FC | [6 empty] | FL |  |  | 0 |  | MEN | FL |  |  | 0 |  |  | 0 | [103 empty] | FC | [5 empty] | 8 | [13 empty] | HOLD |  |  |  | FP |  | 0 |  |  | SS | [6 empty] | FR | R |  | 0 |  |  | MEN | D | 0
2012-12-12 |  | D |  |  | 0 |  |  | HD | T |  | T |  | 8 | [7 empty] | FL |  |  | 0 |  | MEN | FL |  |  | 0 |  |  | 0 | [123 empty] | HOLD |  |  |  | FP |  | 0 |  |  | SS | [6 empty] | FR | R |  | 0 |  |  | MEN | M | 0
2012-12-13 |  | D |  |  | 0 |  |  | HD | T |  | FP |  | 8 | [7 empty] | FL |  |  | 0 |  | MEN | FL |  |  | 0 |  |  | 0 | [123 empty] | HOLD |  |  |  | FC |  | 0 |  |  | SS | [6 empty] | FR | R |  | 0 |  |  | MEN | M | 0
2012-12-14 |  | D |  |  | 0 |  |  | HD | T |  | FP |  | 8 | [7 empty] | CB |  |  | 0 |  | MEN | CB |  |  | 0 |  |  | 0 | [123 empty] | HOLD |  |  |  | FC |  | 0 |  |  | SS | [6 empty] | FR | EWD |  | 0 |  |  | MEN | M | 0
2012-12-15
2012-12-16
2012-12-17 |  | D |  |  | D |  |  | 10 | FP |  | FP |  | 8 | [7 empty] | CB |  |  | D |  | MEN | CB |  |  | M |  |  | MEN | [123 empty] | HOLD | [15 empty] | SF | ELR |  | FR |  |  | 10 | M | 0 |  | Demo | Demo | 12
2012-12-18 |  | D |  |  | D |  |  | 10 | FP |  | FP |  | 8 | [7 empty] | HF |  |  | D |  | MEN | HF |  |  | M |  |  | MEN | [123 empty] | HOLD | [15 empty] | SF | ELR |  | FR |  |  | 10 | T | 0 |  | FR | FR | 12
2012-12-19 |  | M |  |  | D |  |  | 10 | FP |  | FP |  | 8 | [7 empty] | T | HF |  | M |  | MEN | HF | HF |  | M |  |  | MEN | [123 empty] | HOLD | [15 empty] | SF | ELR | PLR | FR |  |  | 10 | T | 0 |  | R | R | 12
2012-12-20 |  | M |  |  | D |  |  | 10 | FC |  | FP |  | 8 | [7 empty] | T | ELF |  | M |  | MEN | T | ELF |  | M |  |  | MEN | [123 empty] | HOLD | [15 empty] | Side | PLR |  | FR |  |  | 10 |  | 0 |  | R | D | 12
2012-12-21 |  | M |  |  | D |  |  | 10 | FC |  | FP |  | 8 | [7 empty] | T | ELF |  | M |  | MEN | T | ELF |  | M |  |  | MEN | [123 empty] | HOLD | [15 empty] | Side | PLR |  | 0 |  |  | 10 |  | 0 |  | R | D | 12
2012-12-22
2012-12-23
2012-12-24 |  | 0 |  |  | 0 |  |  | 0 | [12 empty] | HOLD |  |  | HOLD |  | MEN | 0 |  |  | 0 |  |  | MEN | [123 empty] | HOLD | [18 empty] | HOLD | [7 empty] | HOLD
2012-12-25 |  | 0 |  |  | 0 |  |  | 0 | [12 empty] | HOLD |  |  | HOLD |  | MEN | 0 |  |  | 0 |  |  | MEN | [123 empty] | HOLD | [18 empty] | HOLD
2012-12-26 |  | 0 |  |  | 0 |  |  | 0 | [12 empty] | HOLD |  |  | HOLD |  | MEN | 0 |  |  | 0 |  |  | MEN | [123 empty] | HOLD | [18 empty] | HOLD
2012-12-27 |  | 0 |  |  | 0 |  |  | 0 | [12 empty] | HOLD |  |  | HOLD |  | MEN | 0 |  |  | 0 |  |  | MEN | [123 empty] | HOLD | [18 empty] | HOLD
2012-12-28 |  | 0 |  |  | 0 |  |  | 0 | [12 empty] | HOLD |  |  | HOLD |  | MEN | 0 |  |  | 0 |  |  | MEN | [123 empty] | HOLD | [18 empty] | HOLD
2012-12-29
2012-12-30
2012-12-31 |  | HOLD |  |  | HOLD |  |  | 0 | [12 empty] | HOLD |  |  | HOLD |  | MEN | HOLD |  |  | HOLD |  |  | MEN | [120 empty] | Site |  |  | Site |  |  | SUB | [15 empty] | HOLD
2013-01-01 |  | HOLD |  |  | HOLD |  |  | 0 | [12 empty] | HOLD | [5 empty] | HOLD |  |  | HOLD | [123 empty] | Site |  |  | Site |  |  | SUB | [12 empty] | FR |  |  | FR |  |  | WDS
2013-01-02 |  | HOLD |  |  | HOLD |  |  | 0 | [12 empty] | HOLD | [5 empty] | HOLD |  |  | HOLD | [123 empty] | Site |  |  | Site |  |  | SUB | [12 empty] | FR | R | PLR | FR |  |  | WDS | [13 empty] | Demo | FR | Demo | FR | 8
2013-01-03 |  | HOLD |  |  | HOLD |  |  | 0 | [12 empty] | HOLD | [5 empty] | HOLD |  |  | HOLD | [123 empty] | Site |  |  | Site |  |  | SUB | [12 empty] | R | PLR | ELR | R | PLR | ELR | WDS | [13 empty] | R |  | R |  | 8
2013-01-04 |  | HOLD |  |  | HOLD |  |  | 0 | [12 empty] | FL |  |  | FL | 0 |  | HOLD |  |  | HOLD | [123 empty] | Site |  |  | Site |  |  | SUB | [12 empty] | PLR | ELR |  | PLR | ELR |  | WDS | [13 empty] | R |  | R |  | 8
2013-01-05
2013-01-06
2013-01-07 |  | D |  |  | D |  |  | 9 | [12 empty] | FL |  |  | FL | 0 | 16 | M |  |  | RWK |  |  | 12 | [120 empty] | MAS |  |  | MAS |  |  | WDS | [6 empty] | Demo | R | Demo | FR |  | 10 | ELR |  |  | PLR | ELR |  | WDS | [9 empty] | Site |  | Site | 0 | R |  | 0 | [12 empty] | Demo |  | Demo | FR | MDS | Demo |  | Demo |  | MEN
2013-01-08 |  | M |  |  | M |  |  | 17 | [12 empty] | FL | ELF |  | FL | CB | 16 | IP |  |  | RWK |  |  | 12 | [120 empty] | MAS |  |  | MAS |  |  | WDS | [6 empty] | FR | ELR | FR | I |  | 10 | I |  |  | I |  |  | WDS | [9 empty] | Site |  | Site | 0 | R |  | D | [7 empty] | Demo | EWD | Demo | EWD | 12 | FR |  | FR | R | MDS | FR |  | FR |  | MEN
2013-01-09 |  | M |  |  | M |  |  | 15 | [12 empty] | FL | ELF |  | T | ELF | 16 | IP |  |  | RWK |  |  | 12 | [120 empty] | MAS |  |  | MAS |  |  | WDS | [6 empty] | I | D | D |  |  | 10 | D |  |  | D |  |  | WDS | [9 empty] | Site |  | Site | 0 | D |  | 0 | [7 empty] | Side | EP | Side |  | 12 | FR | R | R |  | MDS | R |  | R |  | MEN
2013-01-10 |  | M |  |  | M |  |  | 9 | [12 empty] | FL |  |  | T | ELF | 16 | FL | ELF |  | IP |  |  | 12 | [120 empty] | MAS |  |  | MAS |  |  | WDS | [6 empty] | D |  | D |  |  | 10 | D |  |  | D |  |  | WDS | [9 empty] | Site |  | Site | 0 | FP | [9 empty] | IP | FP | Side | EP | 12 | R |  |  |  | MDS | R |  | R |  | MEN
2013-01-11 |  | M |  |  | M |  |  | 5 | [12 empty] | T |  |  | T |  | 16 | FL | ELF |  | FL |  |  | 12 | [120 empty] | MAS |  |  | MAS |  |  | WDS | [6 empty] | D |  | D |  |  | 10 | D |  |  | D |  |  | WDS | [9 empty] | Site |  | Site | 0 | FC | [9 empty] | FC |  |  |  |  | R |  |  |  | MDS | R |  | R |  | MEN
2013-01-12
2013-01-13
2013-01-14 |  | M |  |  | M |  |  | 10 | [12 empty] | T |  |  | T |  | 10 | FL | HF |  | FL |  |  | 10 | [120 empty] | MAS |  |  | MAS |  |  | WDS | [6 empty] | M |  | M |  |  | 10 | D |  |  | D |  |  | WDS | [6 empty] | Site | 0 | SUB | Site |  | 0 | SUB | [15 empty] | Side | EP |  |  | MDS | D |  | D |  | 3
2013-01-15 |  | M |  |  | M |  |  | 10 | [12 empty] | T | CT |  | T | CT | 10 | FL | HF | CB | T |  |  | 10 | [120 empty] | MAS |  |  | MAS |  |  | WDS | [6 empty] | M |  | M |  |  | 10 | D |  |  | M |  |  | WDS | [6 empty] | Site | 0 | SUB | Site |  | 0 | SUB | [15 empty] | FP |  |  |  | MDS | D |  | D |  | 3
2013-01-16 |  | M |  |  | M |  |  | 10 | [12 empty] | T | CT |  | T |  | 10 | FL | CB |  | RWK |  |  | 10 | [120 empty] | MAS |  |  | FR |  |  | WDS | [6 empty] | M | R | M |  |  | 10 | M |  |  | M |  |  | WDS | [6 empty] | Site | Site | SUB | Site |  | Site | SUB | [15 empty] | FC |  |  |  | MDS | FP | FC | D |  | 3
2013-01-17 |  | M |  |  | M |  |  | 10 | [12 empty] | T | PLF |  | T | PLF | 10 | FL |  |  | T | CB |  | 10 | [120 empty] | MAS |  |  | FR |  |  | WDS | [6 empty] | M | R | IP |  |  | 10 | M |  |  | 0 |  |  | WDS | [6 empty] | Site | Site | SUB | Site |  | Site | SUB | [22 empty] | FP | FC
2013-01-18 |  | M |  |  | M |  |  | 10 | [12 empty] | T | PLF |  | T | PLF | 10 | T |  |  | T |  |  | 10 | [120 empty] | MAS |  |  | FR |  |  | WDS | [6 empty] | M | R | IP |  |  | 10 | M |  |  | M |  |  | WDS | [6 empty] | Site | 0 | SUB | Site |  | 0 | SUB
2013-01-19
2013-01-20
2013-01-21 |  | M |  |  | FL | ELF |  | 10 | [12 empty] | FP |  |  | FP |  | 10 | T |  |  | T |  |  | 10 | [120 empty] | FR |  |  | FR |  |  | WDS | [6 empty] | IP |  | T |  |  | 10 | M |  |  | 0 |  |  | MDS | [6 empty] | Site | HOLD | SUB | MAS |  | MAS | SUB
2013-01-22 |  | IP |  |  | T | ELF |  | 10 | [12 empty] | FP |  |  | FP |  | 10 | T | CT |  | RWK |  |  | 10 | [120 empty] | FR |  |  | FR |  |  | WDS | [6 empty] | IP |  | T |  |  | 10 | M |  |  | 0 |  |  | MDS | [9 empty] | MAS |  | MAS | SUB | [30 empty] | Demo | Demo | MEN
2013-01-23 |  | IP |  |  | T |  |  | 10 | [12 empty] | FP |  |  | FP |  | 10 | T | CT |  | RWK | CT |  | 10 | [120 empty] | FR |  |  | FR |  |  | WDS | [6 empty] | T |  | T |  |  | 10 | M |  |  | 0 |  |  | MDS | [9 empty] | MAS |  | MAS | MDS | [30 empty] | Demo | Demo | MEN
2013-01-24 |  | FL | ELF |  | T | HF |  | 10 | [12 empty] | FC |  |  | FC |  | 10 | T | PLF |  | RWK | CT |  | 10 | [120 empty] | FR |  |  | FR | R |  | WDS | [6 empty] | T | ELF | T |  |  | 10 | M |  |  | 0 |  |  | MDS | [9 empty] | MAS |  | MAS | WDS | [30 empty] | FR | FR | MEN
2013-01-25 |  | FL | ELF |  | T | HF |  | 10 | [12 empty] | FC |  |  | 0 |  | 0 | T | PLF |  | T | PLF |  | 10 | [120 empty] | FR |  |  | FR | SF |  | WDS | [6 empty] | T | ELF | T |  |  | 10 | M |  |  | 0 |  |  | MDS | [9 empty] | MAS |  | MAS | WDS | [30 empty] | FR | FR | MEN
2013-01-26
2013-01-27
2013-01-28 |  | FL | HF |  | T |  |  | 10 | [18 empty] | FP |  |  | FP |  |  | 10 | [120 empty] | FR | R |  | FR | EWD |  | WDS | [6 empty] | Side | EWD | T |  |  | 10 | M |  |  | 0 |  |  | WDS | [9 empty] | MAS |  | MAS | WDS | [5 empty] | FR |  | FR |  | MDS | [20 empty] | R | R | MEN
2013-01-29 |  | FL | HF | CB | T | CB |  | 10 | [18 empty] | FP |  |  | FP |  |  | 10 | [120 empty] | FR | EWD |  | FR | Side |  | WDS | [6 empty] | EP | FL | FP | FC |  | 10 | IP |  |  | M |  |  | WDS | [9 empty] | MAS |  | FR | WDS | [5 empty] | FR |  | FR |  | MDS | [15 empty] | Demo | FR | Demo | FR | 6 | R | R | MEN
2013-01-30 |  | FL | CB |  | T |  |  | 10 | [18 empty] | FP |  |  | FP |  |  | 10 | [120 empty] | FR | SF |  | ELR | PLR | Side | WDS | [6 empty] | FL |  | FC |  |  | 10 | IP |  |  | 0 |  |  | WDS | [9 empty] | MAS |  | FR | WDS | [5 empty] | FR |  | FR |  | MDS | [15 empty] | FL |  | FL |  | 6 | R | R | MEN
2013-01-31 |  | FL |  |  | FP |  |  | 10 | [18 empty] | FC |  |  | FP |  |  | 10 | [120 empty] | FR | SF |  | ELR | Side |  | WDS | [6 empty] | FP |  | 0 |  |  | 10 | FL | ELF |  | 0 |  |  | WDS | [9 empty] | MAS |  | FR | WDS | [5 empty] | FR |  | FR |  | MDS | [15 empty] | FL |  | FL |  | 6 | R | R | MEN
2013-02-01 |  | T |  |  | 0 |  |  | 10 | [18 empty] | FC |  |  | FC |  |  | 10 | [120 empty] | FR | SF |  | D |  |  | WDS | [6 empty] | FC |  | 0 |  |  | 10 | FL | ELF |  | M |  |  | WDS | [9 empty] | MAS |  | FR | WDS | [5 empty] | FR |  | FR |  | MDS | [15 empty] | FL |  | FL |  | 6 | SF | R | MEN
2013-02-02
2013-02-03
2013-02-04 |  | T |  |  | FP |  |  | 0 | [21 empty] | 0 | [123 empty] | PLR | Side |  | D |  |  | SS | [6 empty] | RWK |  | FL |  |  | 10 | FL | HF |  | M | IP |  | 10 | [9 empty] | FR |  | FR | WDS | [5 empty] | FR |  | FR |  | MDS | [15 empty] | Demo |  | 0 |  | 6 | SF | SF | MEN
2013-02-05 |  | T | CT |  | FP |  |  | 0 | [21 empty] | 0 | [123 empty] | PLR | Side |  | D |  |  | SS | [6 empty] | RWK |  | Demo |  |  | 10 | FL | HF | CB | IP |  |  | 10 | [9 empty] | FR |  | D | WDS | [5 empty] | FR |  | FR |  | MDS | [15 empty] | FL |  | FL |  | 6 | FP | FP | MEN
2013-02-06 |  | T | CT |  | HOLD |  |  | 0 | [21 empty] | 0 | [123 empty] | PLR | Side | ELR | D |  |  | SS | [6 empty] | RWK |  | I | D | R | 10 | FL | CB |  | IP |  |  | 10 | [9 empty] | FR |  | D | WDS | [5 empty] | FR |  | FR |  | MDS | [15 empty] | FL |  | FL |  | 6 | FC | FC | MEN
2013-02-07 |  | T | PLF |  | HOLD |  |  | 0 | [21 empty] | 0 | [123 empty] | ELR | HR | Side | D |  |  | SS | [6 empty] | RWK |  | D |  |  | 10 | FL |  |  | IP |  |  | 10 | [9 empty] | FR |  | D | WDS | [5 empty] | FR |  | 0 |  | MDS | [15 empty] | FL |  | 0 |  | 6
2013-02-08 |  | T | PLF |  | HOLD |  |  | 0 | [21 empty] | 0 | [123 empty] | ELR | HR | Side | D |  |  | SS | [6 empty] | RWK |  | 0 |  |  | 10 | T |  |  | FL |  |  | 10 | [9 empty] | FR |  | D | WDS | [5 empty] | FR |  | FR |  | MDS | [15 empty] | FP | FC |  |  | 6
2013-02-09
2013-02-10
2013-02-11 |  | FP | [27 empty] | FG |  |  | WDS | [120 empty] | I | GTR |  | D |  |  | SS | [6 empty] | RWK |  | FC |  |  | 10 | T |  |  | FL | T |  | 10 | [9 empty] | FR | R | D | WDS | [5 empty] | FR | R | FR | R | MDS
2013-02-12 |  | FP | [27 empty] | FG |  |  | WDS | [120 empty] | D | GTR |  | D |  |  | SS | [6 empty] | RWK |  | M |  |  | 10 | T | CT |  | FL | T |  | 10 | [9 empty] | FR | EWD | M | WDS | [5 empty] | FR | R | FR | R | MDS
2013-02-13 |  | FP | [27 empty] | FG |  |  | WDS | [120 empty] | D |  |  | M |  |  | SS | [6 empty] | RWK |  | M |  |  | 10 | T | CT |  | FL | T |  | 10 | [9 empty] | FR | SF | M | WDS | [5 empty] | FR | R | FR | R | MDS
2013-02-14 |  | FC | [27 empty] | FG |  |  | WDS | [120 empty] | D |  |  | M |  |  | SS | [6 empty] | RWK |  | M |  |  | 10 | T | PLF |  | FL | T |  | 10 | [9 empty] | FR | SF | M | WDS | [5 empty] | FR |  | FR |  | MDS
2013-02-15 |  | FC | [27 empty] | FG |  |  | WDS | [120 empty] | D |  |  | M |  |  | SS | [12 empty] | T | PLF |  | FL | T |  | 10 | [9 empty] | FR | SF | M | WDS | [5 empty] | FR |  | FR |  | MDS

## 2.18.13-5.10.13
CLIENT NAME |  | OP 3 | [6 empty] | OP 2 | [6 empty] | TIFFANY H. | [5 empty] | OP1 | [6 empty] | CLAY M. | [6 empty] | BRANDY S. | [5 empty] | EDITH O. | [5 empty] | PAUL E. |  |  |  |  | MARVIN A. |  |  |  |  | MERLE P. |  |  |  |  | MICHAEL P. |  |  |  |  | WANDA T. | [6 empty] | GEORGE A. |  |  |  | Keith B. | [6 empty] | Albert S. | [6 empty] | Teresa W. | [5 empty] | Leonard S.
ADDRESS |  | 2616 Connor | [6 empty] | 1209 MURPHY | [6 empty] | 106 N. SERGEANT | [5 empty] | 1806 IOWA | [6 empty] | 2024 W 26th | [6 empty] | 2633 S. BYERS | [5 empty] | 1709 MISSOURI | [5 empty] | 2621 S. CONNOR |  |  |  |  | 1616 S.E. MURPHY |  |  |  |  | 2010 HARLEM |  |  |  |  | 1615 VIRGINIA |  |  |  |  | 2627 GRAND | [6 empty] | 2408 EMPIRE |  |  |  | 2022 Pennsylvania | [6 empty] | 2430 Murphy | [6 empty] | 1012 E. 17th | [5 empty] | 1611 Missouri
BUILDING PERMIT |  | 13-0271 | [6 empty] | 13-0264 | [6 empty] | 13-313 | [5 empty] | 13-0270 | [6 empty] | 11-4292 | [6 empty] | 13-0194 | [5 empty] | 12-2492 | [5 empty] | 12-2542 |  |  |  |  | 12-389 |  |  |  |  | 13-356 |  |  |  |  | 13-357 |  |  |  |  | 13-358 | [6 empty] | 13-359 |  |  |  | ? | [6 empty] | 12-508 | [6 empty] | 13-481 | [5 empty] | N/A
PROJECT MANAGER |  | Mark Brown | [6 empty] | Mark Brown | [6 empty] | Brad Mudge | [5 empty] | Brad Mudge | [6 empty] | Darrell Kelley | [6 empty] | Mark Brown | [5 empty] | Darrell Kelley | [5 empty] | Mark Brown |  |  |  |  | Mark Brown |  |  |  |  | Darrell Kelley |  |  |  |  | Darrell Kelley |  |  |  |  | Darrell Kelley | [6 empty] | Darrell Kelley |  |  |  | Darrell Kelley
SITE SUPERVISOR |  | Andrea Cyphers | [6 empty] | Korri Faria | [12 empty] | Rachel Grewe | [6 empty] | Ben Harrison | [6 empty] | Josh Boling | [5 empty] | Zach Bozeman | [5 empty] | Rob Emmett |  |  |  |  | Mark Ward |  |  |  |  | Caity Greig |  |  |  |  | Josh Boling |  |  |  |  | Rachel Grewe | [6 empty] | Nick Sanders |  |  |  | Rob Emmett
CLIENT SERVICES |  | N/A | [6 empty] | N/A | [6 empty] | Danyale Wilson | [5 empty] | N/A | [6 empty] | Brittany Kennell | [6 empty] | Danyale Wilson | [5 empty] | Brittany Kennell | [5 empty] | Brittany Kennell |  |  |  |  | Brittany Kennell |  |  |  |  | Brittany Kennell |  |  |  |  | Lynea Dempsey |  |  |  |  | Brittany Kennell | [6 empty] | Brittany Kennell |  |  |  | Lynea Dempsey
NEW/REMODEL |  | New | [6 empty] | New | [6 empty] | Remodel | [5 empty] | New | [6 empty] | New | [6 empty] | New | [5 empty] | New | [5 empty] | New |  |  |  |  | New |  |  |  |  | Remodel |  |  |  |  | Remodel |  |  |  |  | Remodel | [6 empty] | Remodel |  |  |  | Remodel
| VOLUNTEER # | Projected |  |  | Actual |  |  | Volunteers | Projected |  |  | Actual |  |  | Volunteers | Projected |  |  | Actual |  | Volunteers | Projected |  |  | Actual |  |  | Volunteers | Projected |  |  | Actual |  |  | Volunteers | Projected |  |  | Actual |  | Volunteers | Projected |  |  | Actual |  | Volunteers | Projected |  | Actual |  | Volunteers | Projected |  | Actual |  | Volunteers | Projected |  | Actual |  | Volunteers | Projected |  | Actual |  | Volunteers | Projected |  |  | Actual |  |  | Volunteers | Projected |  | Actual | Volunteers | Projected |  |  | Actual |  |  | Volunteers | Projected |  |  | Actual |  |  | Volunteers | Projected |  | Actual |  |  | Volunteers | Projected |  | Actual |  | Volunteers
2013-02-18 | 40 | [10 empty] | HOLD |  |  |  | Demo |  |  | Demo |  | 20 | FR |  |  | MAS |  |  | WDS | FR |  |  | FR |  |  | MDS | Side | PLR |  | D |  | 10 | D |  |  | M |  | SS | T |  | FL | T | 10
2013-02-19 | 40 | [14 empty] | Demo |  |  | Demo |  | 20 | FR |  |  | FR |  |  | WDS | FR |  |  | FR |  |  | MDS | Side | PLR |  | M |  | 10 | M |  |  | M |  | SS | T | CT | FL | T | 10
2013-02-20 | 40 | [14 empty] | Demo |  |  | Demo |  | 20 | FR |  |  | FR |  |  | WDS | FR |  |  | FR |  |  | MDS | Side | PLR | ELR | M |  | 10 | M |  |  | M |  | SS | T | CT | FL | T | 10
2013-02-21 | 40 | [14 empty] | Demo |  |  | 0 |  | 20 | FR |  |  | 0 |  |  | WDS | FR | EWD |  | 0 |  |  | MDS | Side | ELR | HR | 0 |  | 10 | M |  |  | 0 |  | SS | T | PLF | 0 |  | 10
2013-02-22 | 40 | [14 empty] | Demo |  |  | Demo |  | 20 | FR |  |  | FR |  |  | WDS | FR | EWD |  | FR |  |  | MDS | Side | ELR | HR | M |  | 10 | M |  |  | M |  | SS | T | PLF | FL | T | 10
2013-02-23 | 0
2013-02-24 | 0
2013-02-25 | 20 | [14 empty] | FR |  |  | 0 |  | IH | FR |  |  | FR |  |  | WDS | FR | EWD |  | FR |  |  | MDS | I | GTR |  | M |  | 10 | M |  |  | M |  | SS | FP |  | FL | T | 10
2013-02-26 | 20 | [14 empty] | FR |  |  | 0 |  | IH | FR |  |  | 0 |  |  | WDS | FR | EWD |  | 0 |  |  | MDS | D | GTR |  | 0 |  | 10 | M |  |  | 0 |  | SS | FP |  | 0 |  | 10
2013-02-27 | 20 | [14 empty] | FR |  |  | 0 |  | IH | FR |  |  | 0 |  |  | WDS | FR |  |  | 0 |  |  | MDS | D |  |  | M |  | 10 | M |  |  | M |  | SS | FP |  | FL | T | 10
2013-02-28 | 20 | [14 empty] | FR |  |  | 0 |  | IH | FR |  |  | FR |  |  | WDS | FR |  |  | FR |  |  | MDS | D |  |  | M |  | 10 | M |  |  | M |  | SS | FC |  | FP | CB | 10
2013-03-01 | 20 | [14 empty] | FR |  |  | FR |  | IH | FR |  |  | FR |  |  | WDS | FR |  |  | 0 |  |  | MDS | D |  |  | M |  | 10 | M |  |  | M |  | SS | FC |  | FP |  | 10
2013-03-02 | 0
2013-03-03 | 0
2013-03-04 | 56 | Site |  |  | Site |  |  | WDS | MAS |  |  | 0 |  |  | WDS | FR |  |  | FR |  | IH | Side | PLR |  | FR | R |  | 10 | PLR |  |  | FR |  |  | MDS | D |  |  | M |  | 10 | M |  |  | M |  | SS |  |  | FL | T |  | RWK | FP | RWK | FP | 6 | [5 empty] | Demo |  | Demo |  | 10 | Demo |  |  | Demo |  |  | 10 | Demo |  |  | 10
2013-03-05 | 56 | Site |  |  | Site |  |  | WDS | MAS |  |  | 0 |  |  | WDS | FR | EWD |  | FR |  | IH | Side | PLR |  | FR | R |  | 10 | PLR |  |  | FR |  |  | MDS | M |  |  | IP |  | 10 | IP |  |  | M |  | SS |  |  | RWK |  |  | RWK | FP | RWK | FP | 6 | [5 empty] | FR |  | Demo |  | 10 | FR |  |  | FR | D |  | 10 | Demo |  | Demo | 10
2013-03-06 | 66 | Site |  |  | MAS |  |  | WDS | MAS |  |  | 0 |  |  | WDS | FR | SF |  | FR |  | IH | Side | PLR | ELR | SF | PLR | ELR | 10 | PLR | ELR |  | FR |  |  | MDS | M |  |  | IP |  | 10 | IP |  |  | M |  | SS |  |  | RWK |  |  | RWK | FP | RWK | FP | 6 | Demo |  |  |  | 10 | R | ELR | Demo |  | 10 | R | MAS |  | D | M |  | 10 | Demo |  | Demo | 10
2013-03-07 | 66 | Site |  |  | 0 |  |  | WDS | MAS |  |  | 0 |  |  | WDS | FR | SF |  | FR |  | IH | Side | ELR | HR | SF | PLR | ELR | 10 | ELR | HR |  | FR |  |  | MDS | M |  |  | FL |  | 10 | FL |  |  | M |  | SS |  |  | RWK |  |  | RWK | FP | RWK | FP | 6 | Demo |  |  |  | 10 | Side | PLR | ??? |  | 10 | EWD | Side |  | M | FL | R | 10 | Demo |  |  | 10
2013-03-08 | 66 | Site |  |  | 0 |  |  | WDS | MAS |  |  | 0 |  |  | WDS | FR | SF |  | FR |  | IH | Side | ELR | HR | ELR | PLR |  | 10 | ELR | HR |  | FR |  |  | MDS | M |  |  | FL |  | 10 | FL |  |  |  |  | SS |  |  | FP | FC |  | RWK | FP | RWK | FP | 6 | FR |  |  |  | 10 | I |  | ??? |  | 10 | ELR | PLR |  | M | FL |  | 10 | Demo |  |  | 10
2013-03-09 | 0
2013-03-10 | 0
2013-03-11 | 86 | MAS |  |  | 0 |  |  | WDS | MAS |  |  | MAS |  |  | WDS | Side | PLR |  | FR |  | 10 | I | GTR |  | HR |  |  | 10 | I |  |  | FR |  |  | MDS | M |  |  | FL |  | 10 | FL | ELF | HF | M |  | SS |  |  | HOLD |  |  | RWK | FP | RWK | FP | 6 | FR |  | Demo |  | 10 | D |  | Demo |  | 10 | I | HR |  | IP | T |  | 10 | FR |  | Demo | 10 | Demo |  |  | Demo |  |  | 10
2013-03-12 | 86 | MAS |  |  | 0 |  |  | WDS | MAS |  |  | MAS |  |  | WDS | Side | PLR |  | FR |  | 10 | D | GTR |  | HR |  |  | 10 | I |  |  | FR |  |  | MDS | M |  |  | FL |  | 10 | FL | ELF | CB | IP |  | SS | [5 empty] | RWK | FP | RWK | FP | 6 | R | EWD | FR | R | 10 | M |  | ??? |  | 10 | D |  |  | ??? |  |  | 10 | FR |  | Demo | 10 | Demo |  |  | Demo |  |  | 10
2013-03-13 | 76 | MAS |  |  | 0 |  |  | WDS | MAS |  |  | MAS |  |  | WDS | Side | PLR | ELR | FR |  | 10 | D |  |  | ELR |  |  | 0 | D |  |  | FR |  |  | MDS | M |  |  | FL |  | 10 | FL | CB |  | 0 |  | SS | [5 empty] | RWK | FP | RWK | FP | 6 | SF | Side | FR | R | 10 | M |  | ??? |  | 10 | D |  |  | T |  |  | 10 | FR |  | ??? | 10 | Demo |  |  | Demo |  |  | 10
2013-03-14 | 86 | MAS |  |  | 0 |  |  | WDS | MAS |  |  | MAS |  |  | WDS | Side | ELR | HR | FR |  | 10 | D |  |  | Side |  |  | 10 | D |  |  | FR |  |  | MDS | M |  |  | T |  | 10 | FL |  |  | 0 |  | SS | [5 empty] | RWK | FP | RWK | FP | 6 | I |  | FR | R | 10 | M |  | D |  | 10 | M |  |  | RWK | FP |  | 10 | FR |  | Demo | 10 | Demo |  |  | Demo |  |  | 10
2013-03-15 | 86 | MAS |  |  | 0 |  |  | WDS | MAS |  |  | MAS |  |  | WDS | Side | ELR | HR | FR |  | 10 | D |  |  | Side | I |  | 10 | D |  |  | FR |  |  | MDS | M |  |  | T |  | 10 | T |  |  | FL |  | SS | [5 empty] | RWK | FP | RWK | FP | 6 | D |  | I | D | 10 | M |  | ??? |  | 10 | M |  |  | FP | FC |  | 10 | FR |  | Demo | 10 | Demo |  |  | Demo |  |  | 10
2013-03-16 | 0
2013-03-17 | 0
2013-03-18 | 76 | MAS |  |  | 0 |  |  | WDS | FR |  |  | FR |  |  | WDS | I | GTR |  | FR |  | 10 | D |  |  | D |  |  | 10 | D |  |  | FR | ELR | PLR | MDS | M |  |  | T |  | 10 | T |  |  | FL |  | SS | [5 empty] | RWK | FP | RWK | FP | 6 | M |  | M |  | 10 | M |  | D | M | 10 | M | [6 empty] | PLR |  | HOLD | 10 | FR |  |  | FR |  |  | 10
2013-03-19 | 76 | MAS |  |  | 0 |  |  | WDS | FR |  |  | FR |  |  | WDS | D | GTR |  | FR |  | 10 | M |  |  | D |  |  | 10 | D |  |  | FR | ELR | PLR | MDS | IP |  |  | T |  | 10 | T | CT |  | FL |  | SS | [5 empty] | RWK | FP | RWK | FP | 6 | M |  | M |  | 10 | IP |  | M |  | 10 | M | [6 empty] | PLR |  |  | 10 | FR |  |  | FR |  |  | 10
2013-03-20 | 76 | MAS |  |  | 0 |  |  | WDS | FR |  |  | FR |  |  | WDS | D |  |  | FR |  | 10 | M |  |  | D |  |  | 10 | D |  |  | FR | ELR | PLR | MDS | IP |  |  | T |  | 10 | T | CT |  | FL |  | SS | [5 empty] | RWK | FP | RWK | FP | 6 | M |  | M |  | 10 | FL |  | M |  | 10 | M | [6 empty] | PLR | ELR |  | 10 | I |  |  | I |  |  | 10
2013-03-21 | 76 | MAS |  |  | 0 |  |  | WDS | FR |  |  | FR |  |  | WDS | D |  |  | FR |  | 10 | M |  |  | D |  |  | 10 | D |  |  | 0 |  |  | MDS | FL |  |  | T |  | 10 | T | PLF |  | FL |  | SS | [5 empty] | RWK | FP | RWK | FP | 6 | M |  | ??? |  | 10 | T |  | ??? |  | 10 | IP | [6 empty] | ELR | HR |  | 10 | I |  |  | I |  |  | 10
2013-03-22 | 76 | MAS |  |  | 0 |  |  | WDS | FR | R |  | 0 |  |  | WDS | D |  |  | FR |  | 10 | M |  |  | D |  |  | 10 | D |  |  | 0 |  |  | MDS | FL |  |  | T |  | 10 | T | PLF |  | FL |  | SS | [5 empty] | RWK | FP | RWK | FP | 6 | M |  | M | Demo | 10 | T |  | ??? |  | 10 | FL | [6 empty] | ELR | HR |  | 10 | D |  |  | D |  |  | 10
2013-03-23 | 0
2013-03-24 | 0
2013-03-25 | 76 | FR |  |  | 0 |  |  | WDS | FR | R |  | 0 |  |  | 10 | D |  |  | FR |  | 10 | M |  |  | D |  |  | 10 | D |  |  | ELR | PLR |  | MDS | FL | ELF | HF | FP | FC | 10 | FP |  |  | FL | CB | SS | [5 empty] | RWK | FP | RWK | FP | 6 | IP |  | D | M | 10 | CB | CT | ??? |  | SUB | T | ELF | PLF |  |  |  |  | I |  |  | 10 | D |  |  | D |  |  | 10
2013-03-26 | 76 | FR |  |  | 0 |  |  | WDS | FR | EWD |  | 0 |  |  | 10 | M |  |  | FR |  | 10 | M |  |  | D |  |  | 10 | IP |  |  | PLR |  |  | MDS | FL | ELF | CB | HOLD |  | 10 | FP |  |  | ELF |  | SS | [5 empty] | RWK | FP | RWK | FP | 6 | FL |  |  |  | 10 | PLF |  | ??? |  | IH | T | [6 empty] | D |  |  | 10 | D |  |  | D |  |  | 10
2013-03-27 | 76 | FR |  |  | 0 |  |  | WDS | FR | SF |  | 0 |  |  | 10 | M |  |  | FR |  | 10 | M |  |  | D | M |  | 10 | IP |  |  | ELR | PLR |  | MDS | FL | CB |  |  |  | 10 | FP |  |  | T |  | SS | [5 empty] | RWK | FP | RWK | FP | 6 | T |  |  |  | 10 | ELF |  | ??? |  | IH | T | HF | [5 empty] | D |  |  | 10 | D |  |  | D |  |  | 10
2013-03-28 | 76 | FR |  |  | 0 |  |  | WDS | FR | SF |  | 0 |  |  | 10 | M |  |  | FR |  | 10 | M |  |  | M |  |  | 10 | FL |  |  | ELR | PLR |  | MDS | FL |  |  |  |  | 10 | FC |  |  | T |  | SS | [5 empty] | RWK | FP | RWK | FP | 6 | T |  |  |  | 10 | FP |  | M |  | IH | FP | [6 empty] | D |  |  | 10 | D |  |  | D |  |  | 10
2013-03-29 | 76 | FR | R |  | 0 |  |  | WDS | FR | SF |  | 0 |  |  | 10 | M |  |  | FR |  | 10 | M |  |  | M |  |  | 10 | FL |  |  | ELR | PLR |  | MDS | T |  |  |  |  | 10 | FC |  |  | T |  | SS | [5 empty] | RWK | FP | RWK | FP | 6 | T |  |  |  | 10 | FC |  | ??? |  | IH | FC | [6 empty] | D |  |  | 10 | D |  |  | D |  |  | 10
2013-03-30 | 0
2013-03-31 | 0 | RECOV | [6 empty] | RECOV | [6 empty] | RECOV | [12 empty] | RECOV | [12 empty] | RECOV | [15 empty] | RWK |  |  |  |  | RWK
2013-04-01 | 68 | MAS |  |  | MAS |  |  | MEN | FR |  |  | FR |  |  | 10 | FR |  |  | FR |  | 10 | M |  |  | M |  |  | 10 | FR | EWD |  | 0 |  |  | 10 | T |  |  |  |  | 0 | T |  |  | T |  | SS | [5 empty] | RWK | FP | RWK | FP | 6 | M |  |  |  | 6 | IP |  | Side | M | 6 | [11 empty] | D |  |  | D |  |  | 10
2013-04-02 | 68 | MAS |  |  | 0 |  |  | MEN | FR |  |  | FR |  |  | 10 | FR |  |  | FR |  | 10 | IP |  |  | M |  |  | 10 | FR | EWD |  | FR | EWD |  | 10 | T | CT |  |  |  | 0 | T | CT |  | T | CT | SS | [5 empty] | RWK | FP | RWK | FP | 6 | M |  |  |  | 6 | IP |  | Side | IP | 6 | [11 empty] | M |  |  | M |  |  | 10
2013-04-03 | 68 | MAS |  |  | MAS |  |  | MEN | FR |  |  | FR |  |  | 10 | FR |  |  | FR |  | 10 | IP |  |  | M | MAS |  | 10 | FR | EWD |  | FR | EWD |  | 10 | T | CT |  |  |  | 0 | T | CT |  | T | CT | SS | [5 empty] | RWK | FP | RWK | FP | 6 | M |  | D | FR | 6 | IP |  | IP | T | 6 | [11 empty] | M |  |  | M |  |  | 10
2013-04-04 | 68 | MAS |  |  | MAS |  |  | MEN | FR |  |  | FR |  |  | 10 | FR |  |  | FR |  | 10 | FL |  |  | M | MAS |  | 10 | FR | EWD |  | FR | EWD |  | 10 | T | PLF |  |  |  | 0 | T | PLF |  | T | PLF | SS | [5 empty] | RWK | FP | RWK | FP | 6 | IP |  | D |  | 6 | FL |  | Side | FL | 6 | [11 empty] | M |  |  | M |  |  | 10
2013-04-05 | 68 | MAS |  |  | MAS |  |  | MEN | FR |  |  | FR |  |  | 10 | FR |  |  | FR |  | 10 | FL |  |  | M |  |  | 10 | FR | EWD |  | FR | EWD |  | 10 | T | PLF |  |  |  | 0 | T | PLF |  |  |  | SS | [5 empty] | RWK | FP |  |  | 6 | IP |  | D |  | 6 | FL |  | FL | ELF | 6 | [11 empty] | M | [5 empty] | 10
2013-04-06 | 0
2013-04-07 | 0 | [73 empty] | RECOV
2013-04-08 | 58 | MAS |  |  | 0 |  |  | MEN | R | PLR |  | FR |  |  | 10 | FR | MAS |  | FR |  | 10 | FL | ELF | HF | Side | IP |  | 10 | HR | ELR |  | 0 |  |  | 0 | FP |  |  |  |  | 0 | FP |  |  | FP |  | SS | [5 empty] | RWK | FP | RWK | FP | 6 | FL |  | M | SF | 6 | FL | ELF | FL | T | 6 | [7 empty] | Site |  | 0 | SUB | M |  |  | M |  |  | 10
2013-04-09 | 58 | MAS |  |  | FR |  |  | MEN | R | PLR |  | FR | R |  | 10 | FR | MAS |  | FR |  | 10 | FL | ELF | CB | FL |  |  | 10 | HR | ELR |  | 0 |  |  | 0 | FP |  |  |  |  | 0 | FP |  |  | FP |  | SS | [5 empty] | RWK | FP | RWK | FP | 6 | FL | ELF | M | T | 6 | T | CB | Side | T | 6 | [7 empty] | Site |  | 0 | SUB | M |  |  | M |  |  | 10
2013-04-10 | 68 | MAS |  |  | 0 |  |  | MEN | SF | PLR | ELR | 0 |  |  | 10 | FR | MAS |  | FR |  | 10 | FL | CB |  | FL |  |  | 10 | HR | FR |  | 0 |  |  | 10 | FP |  |  |  |  | 0 | FP |  |  | FP | FC | SS | [5 empty] | RWK | FP | RWK | FP | 6 | FL |  | M | T | 6 | T | CB | T |  | 6 | [7 empty] | Site |  | Site | SUB | M |  |  | M |  |  | 10
2013-04-11 | 68 | MAS | FR |  | FR |  |  | MEN | SF | ELR | HR | 0 |  |  | 10 | FR | MAS |  | FR |  | 10 | FL |  |  | FL |  |  | 10 | FR |  |  | 0 |  |  | 10 | FC |  |  |  |  | 0 | FC |  |  | FP | FC | SS | [5 empty] | RWK | FP |  |  | 6 | T |  | D |  | 6 | T | R | T |  | 6 | [7 empty] | Site |  | 0 | SUB | M |  |  | M |  |  | 10
2013-04-12 | 68 | MAS | FR |  | FR |  |  | MEN | SF | ELR | HR | FR |  |  | 10 | EWD |  |  | FR |  | 10 | T |  |  | FL | T |  | 10 | FR |  |  | 0 |  |  | 10 | FC |  |  |  |  | 0 | FC |  |  |  |  | SS | [5 empty] | RWK | FP |  |  | 6 | T | FL | M | T | 6 | T | R | 0 |  | 6 | [7 empty] | Site |  | 0 | SUB | M |  |  | IP |  |  | 10
2013-04-13 | 0
2013-04-14 | 0
2013-04-15 | 82 | FR |  |  | FR |  |  | 10 | Side | I |  | R | PLR |  | 20 | SF | PLR |  | FR |  | 10 | T |  |  | T | CB |  | 10 | I |  |  | FR |  |  | 10 | [22 empty] | T | PLF | 0 |  | 6 | T | CT | FP |  | 6 | [7 empty] | RECOV |  | RECOV | SUB | M |  |  | IP |  |  | 10
2013-04-16 | 82 | FR |  |  | FR |  |  | 10 | Side | D |  | R | PLR |  | 20 | SF | PLR |  | FR |  | 10 | T | CT |  | T | CB |  | 10 | I |  |  | FR |  |  | 10 | [22 empty] | T |  | RWK | FP | 6 | FP |  | 0 |  | 6 | [10 empty] | SUB | IP |  |  | FL |  |  | 10
2013-04-17 | 82 | FR |  |  | FR |  |  | 10 | Side | D |  | SF | PLR | ELR | 20 | SF | PLR | HR | FR |  | 10 | T | CT |  | T |  |  | 10 | D |  |  | FR |  |  | 10 | [22 empty] | FP |  | RWK | FP | 6 | FP |  | 0 |  | 6 | [10 empty] | SUB | IP |  |  | FL |  |  | 10
2013-04-18 | 82 | FR |  |  | FR |  |  | 10 | Side | D |  | SF | PLR | ELR | 20 | SF | ELR | HR | FR | EWD | 10 | T | PLF |  | T |  |  | 10 | D |  |  | FR |  |  | 10 | [22 empty] | FP |  | 0 |  | 6 | FP | PLF | 0 |  | 6 | [10 empty] | SUB | FL |  |  | FL |  |  | 10
2013-04-19 | 82 | FR | R |  | FR |  |  | 10 | Side | D |  | SF | I | HR | 20 | SF | ELR | HR | FR | EWD | 10 | T | PLF |  | 0 |  |  | 10 | D |  |  | FR |  |  | 10 | [22 empty] | FC |  | 0 |  | 6 | FC |  | 0 |  | 6 | [10 empty] | SUB | FL |  |  | FL |  |  | 10
2013-04-20 | 0
2013-04-21 | 0
2013-04-22 | 96 | FR | R |  | FR |  |  | 10 | D | GTR |  | Side | I |  | 10 | Side | I |  | FR | PLR | 20 | FP |  |  | FP |  |  | 10 | D |  |  | FR |  |  | 10 | [39 empty] | Site |  |  | SUB | FL | ELF | HF | T |  |  | 10 | Demo |  |  | Demo |  |  | 15 | SF | EP | T | FL |  | 8 | I | D | I | D | 3
2013-04-23 | 96 | FR | EWD |  | FR |  |  | 10 | M | GTR |  | D |  |  | 10 | Side | I |  | FR | PLR | 20 | FP |  |  | FP |  |  | 10 | D |  |  | FR |  |  | 10 | [39 empty] | Site |  |  | SUB | FL | ELF | CB | T |  |  | 10 | Demo |  |  | Demo | FR |  | 15 | SF | EP | T | M |  | 8 | M |  | M |  | 3
2013-04-24 | 96 | FR | SF |  | FR |  |  | 10 | M |  |  | D |  |  | 10 | Side | D |  | FR | PLR | 20 | FP |  |  | FP |  |  | 10 | D |  |  | FR | PLR |  | 10 | [39 empty] | Site |  |  | SUB | FL | CB |  | T |  |  | 10 | Demo |  |  | Demo | FR |  | 15 | SF | PLR | T | M | FR | 8 | M |  | M |  | 3
2013-04-25 | 96 | FR | SF |  | FR | R |  | 10 | M |  |  | D |  |  | 10 | Side | D |  | FR |  | 20 | FC |  |  | FC |  |  | 10 | FL | ELF |  | FR | PLR |  | 10 | [39 empty] | Site |  |  | SUB | FL |  |  | T |  |  | 10 | Demo |  |  |  | FR |  | 15 | SF | ELR | T | M | FL | 8 | IP |  | IP |  | 3
2013-04-26 | 96 | FR | SF |  | FR | R |  | 10 | M |  |  | D |  |  | 10 | Side | D |  | FR |  | 20 | FC |  |  | FC |  |  | 10 | FL | ELF |  | FR | PLR |  | 10 | [39 empty] | Site |  |  | SUB | T |  |  | T |  |  | 10 | Demo |  |  |  | FR |  | 15 | SF | HR | FL |  |  | 8 | FP | FC | FP | FC | 3
2013-04-27 | 0
2013-04-28 | 0
2013-04-29 | 74 | Side | PLR |  | FR | R | PLR | 10 | M |  |  | D | Side |  | 10 | D |  |  | FR |  | 10 |  |  |  | FG |  |  |  | FL | ELF | HF | FR | HR | ELR | 10 | [39 empty] | MAS |  |  | 10 | T |  |  | T | CB |  | 10 | FR |  |  |  | FR |  | 6 | Side | D | M |  |  | 8
2013-04-30 | 74 | Side | PLR |  | SF | PLR |  | 10 | M |  |  | D |  |  | 10 | D |  |  | FR |  | 10 | [7 empty] | T | HF | CB | FR | HR | ELR | 10 | [39 empty] | MAS |  |  | 10 | T | CT |  | T |  |  | 10 | FR |  |  |  | FR |  | 6 | Side | D | M | D | FL | 8
2013-05-01 | 74 | Side | PLR | ELR | SF | PLR | ELR | 10 | M |  |  | D |  |  | 10 | M |  |  | FR |  | 10 | [7 empty] | T | CB |  | FR | HR | ELR | 10 | [39 empty] | MAS |  |  | 10 | T | CT |  | T | FL | RWK | 10 | FR |  |  | SF |  |  | 6 | Side | M | M | Side |  | 8
2013-05-02 | 74 | Side | ELR | HR | SF | ELR |  | 10 | M |  |  | D |  |  | 10 | M |  |  | FR |  | 10 | [7 empty] | T | PLF |  | FR | HR | ELR | 10 | [39 empty] | MAS |  |  | 10 | T | PLF |  | T |  | RWK | 10 | FR | EWD |  | SF | Side |  | 6 | Side | M | M | Side |  | 8
2013-05-03 | 74 | Side | ELR | HR | SF | ELR | HR | 10 | M |  |  | M |  |  | 10 | M |  |  | FR |  | 10 | [7 empty] | T | PLF |  | FR | I |  | 10 | [39 empty] | MAS |  |  | 10 | T | PLF |  | T |  | RWK | 10 | FR | EWD |  |  | Side |  | 6 | Side | M | M | Side |  | 8
2013-05-04 | 0
2013-05-05 | 0
2013-05-06 | 74 | I | GTR |  | SF |  |  | 10 | M |  |  | M |  |  | 10 | M |  |  | FR | ELR | 10 |  |  |  |  | CT |  |  | FP |  |  | D |  |  | 10 | [39 empty] | MAS |  |  | 10 | FP |  |  | T | CB | RWK | 10 | SF | PLR |  |  | Side |  | 6 | M |  | M |  |  | 8
2013-05-07 | 74 | D | GTR |  | FR | I |  | 10 | IP |  |  | M |  |  | 10 | M |  |  | FR | ELR | 10 |  |  |  |  | PLF |  |  | FP |  |  | D |  |  | 10 | [39 empty] | MAS |  |  | 10 | FP |  |  | T | CB | RWK | 10 | SF | PLR |  |  | Side |  | 6 | M |  | M |  |  | 8
2013-05-08 | 74 | D |  |  | FR | I | Side | 10 | IP |  |  | M |  |  | 10 | M |  |  | FR | ELR | 10 | [7 empty] | FP |  |  | D |  |  | 10 | [39 empty] | MAS |  |  | 10 | FP |  |  | T |  | RWK | 10 | SF | PLR | ELR |  | 0 |  | 6 | IP |  | M |  |  | 8
2013-05-09 | 74 | D |  |  | FR | I | Side | 10 | FL |  |  | M |  |  | 10 | M |  |  | FR | HR | 10 | [7 empty] | FC |  |  | D | M |  | 10 | [39 empty] | MAS |  |  | 10 | FC |  |  |  |  | RWK | 10 | SF | ELR | HR |  | Side | FR | 6 | IP |  | Side | PLR | ELR | 8
2013-05-10 | 74 | D |  |  | FR | I | Side | 10 | FL |  |  | M |  |  | 10 | M |  |  | FR | MAS | 10 | [7 empty] | FC |  |  | D | M |  | 10 | [39 empty] | MAS |  |  | 10 | FC |  |  | PLF | FP |  | 10 | SF | ELR | HR |  | Side |  | 6 | FC |  | IP |  |  | 8
2013-05-11
2013-05-12

## 5.13.13-8.2.13
CLIENT NAME |  | Name |  |  | Name Here
ADDRESS |  | Address |  |  | Address Here
BUILDING PERMIT |  | Permit Number |  |  | Building permit number
PROJECT MANAGER
SITE SUPERVISOR
CLIENT SERVICES
NEW/REMODEL
| VOLUNTEER # | Projected | Actual | Volunteers | Projected | Actual | Volunteers | Projected | Actual | Volunteers | Projected | Actual | Volunteers | Projected | Actual | Volunteers | Projected |  |  | Actual | Volunteers | Projected | Actual |  | Volunteers
[16 empty] | 16 | FL |  |  |  | 8 |  | D | M
[16 empty] | 16 | FL | CB |  |  | 8 |  | D | M
[16 empty] | 16 | FL | CB |  |  | 8 |  | D
[16 empty] | 16 | FL |  |  |  | 8
[16 empty] | 16 | FL |  |  |  | 8
[16 empty] | 10 | T | ELF |  |  | 8
[16 empty] | 10 | T | CT |  |  | 8
[16 empty] | 10 | T | CT |  |  | 8
[16 empty] | 10 | T | PLF |  |  | 8
[16 empty] | 10 | T | PLF | HF |  | 8
[16 empty] | 10 | FP |  |  |  | 8
[16 empty] | 10 | FP |  |  |  | 8
[16 empty] | 10 | FP |  |  |  | 8
[16 empty] | 10 | FC |  |  |  | 8
[16 empty] | 10 | FC |  |  |  | 8
10
10
10
10
10
10
10
10
10
10
10
10
10
10
10